## Proj Assess Report
Project Assessment Report
Version 2.5
To ensure a consistent reporting approach and terminology used across IT projects and across agencies statewide, this template and rating scale must be used for quarterly reporting without modification. Items (1) through (1e) will be reported from two perspectives: "rear view" and "forward view". Rear view refers to project status to date. "Forward view" refers to expectations in the future. Items (2) through (2f) will be reported in the context of the "forward view" only. A second tab ("Re-baseline History") has been added to this template and is required for all projects. This tab is for agency reporting only, and is not required for iQMS contractor submissions.
Project Name:
Agency Name:
Person completing this form and affiliation:
Reporting Period:
Date when form was completed:
Technology Description
Platforms:
% custom:
Funding Description
|  | Rating (rear view) | Rating (fwd view) | Explanation | Rating Scale^
1 | Overall Project Health |  |  |  | Red, yellow, green*
1a | Total Cost (Budget) |  |  |  | Red, yellow, green*
1b | Schedule |  |  |  | Red, yellow, green*
1c | Scope |  |  |  | Red, yellow, green*
1d | Resource |  |  |  | Red, yellow, green*
1e | Deliverables (Work Products) Quality |  |  |  | Red, yellow, green*
2 | Overall Delivery Risk | N/A |  |  | high, medium, low*
2a | Buusiness Case | N/A |  |  | high, medium, low*
2b | Technology | N/A |  |  | high, medium, low*
2c | Funding | N/A |  |  | high, medium, low*
2d | Business Transition | N/A |  |  | high, medium, low*
2e | Long-Term Supportability | N/A |  |  | high, medium, low*
2f | Long-Term Maintainability | N/A |  |  | high, medium, low*
Notes:
^ | See below for description of scale.
* | Explanation not required when "green" or "low".
1 | Overall Project Health
Green = No individual health indicators are red, and no more than one individual health indicator is yellow. No critical issues are impacting ability to meet documented objectives.
Yellow = No individual health indicators are red, and two or more individual health indicators are yellow. Explanation must include action plan to mitigate areas in yellow.
Red = One or more individual health indicators are red. Explanation must include action plan to mitigate areas in red or yellow.
1a | Total Cost (Budget)
Green = Actual is (is expected to be) less than 5% different (+/-) from the approved budget baseline, as reported on Project Variance Report.
Yellow = Actual is (is expected to be) 5-15% different (+/-) from approved budget baseline, as reported on Project Variance Report.
Red = Actual is (is expected to be) more than 15% different (+/-) from approved budget baseline, as reported on Project Variance Report.
1b | Schedule
Green = Progress is (is expected to be) on schedule or less than 5% behind approved schedule baseline, as reported on Project Variance Report.
Yellow = Project completion is (is expected to be) delayed with the project duration 5-15% behind approved schedule baseline, as reported on Project Variance Report.
Red = Project completion is (is expected to be) delayed with project duration more than 15% behind approved schedule baseline, as reported on Project Variance Report.
1c | Scope
Green = All deliverables fulfill (are expected to fulfill) stated requirements.
Yellow = At least one deliverable does not fulfill (is not expected to fulfill) stated requirements.
Red = More than one deliverable does not fulfill (are not expected to fulfill) stated requirements.
1d | Resource
Green = All resources needed by internal and contractor staff are (are expected to be) available.
Yellow = Almost all resources needed by internal and contractor staff are (are expected to be) available.
Red = Almost all resources needed by internal and contractor staff are (are expected to be) unavailable.
1e | Deliverables (Work Products) Quality |  | (Work Products include all planning and design artifacts.)
Green = All deliverables are (are expected to be) "fit to use".
Yellow = At least one deliverables is (is expected to be) not "fit to use".
Red = More than one deliverable is not (is not expected to be)"fit to use".
2 | Overall Delivery Risk
Low = No individual risk indicators are red, and no more than one individual risk indicator is yellow. No critical issues are impacting ability to meet documented objectives.
Medium = No individual risk indicators are red, and two or more individual risk indicators are yellow. Explanation must include action plan to mitigate areas in yellow.
High = One or more individual risk indicators are red. Explanation must include action plan to mitigate areas in red or yellow.
2a | Business Case
Low = There is no reason to think that the original business case & ROI targets (if exist) cannot be achieved.
Medium = There is some reason to think that the original business case & ROI targets (if exist) cannot be achieved.
High = There are many reasons to think that the original business case & ROI targets (if exist) cannot be achieved.
2b | Technology
Low = All technology employed (including development and testing tools) are stable.
Medium = Almost all technology employed (including development and testing tools) are stable.
High = Almost all technology employed (including development and testing tools) are unstable.
2c | Funding
Low = All future tasking requires resources that are expected to be available.
Medium = Almost all future tasking requires resources that are expected to be available.
High = Almost all future tasking requires resources that are expected to be unavailable.
2d | Business Transition
Low = Business transition and disruption are well planned with few surprises to business operations expected.
Medium = Business transition and disruption are planned, but surprises to business operations are expected.
High = Business transition and disruption are not planned with surprises to business operations expected.
2e | Supportability |  | (work required to ensure proper operation of specified system functions)
Low = All aspects of the IT investment are supportable in the long-run.
Medium = Most aspects of the IT investment are supportable in the long-run.
High = Many aspects of the IT investment are not supportable in the long-run.
2f | Maintainability |  | (work required to enhance specified system functions)
Low = All aspects of the IT investment are maintainable in the long-run.
Medium = Most aspects of the IT investment are maintainable in the long-run.
High = Many aspects of the IT investment are not maintainable in the long-run.
Updated Feb2025

## Re-baseline History
Re-baseline History
Project Name:
Agency Name:
Person completing this form and affiliation:
Reporting period:
Date form was completed:
Add a line to the table for the initial baseline and each approved re-baseline. Enter N/A if a particular category is not applicable or did not change.
Reason for Change | Planning End Date | Implementation / Go Live Date | Project Closing End Date | Scope Change | Budget Change | Baseline Change Approval Date | Baseline Approved By
Original project baseline | [enter date] | [enter date] | [enter date] | N/A | N/A | Initial approval: [enter date] | [e.g., ESC]
[enter reason for re-baseline] | [enter date] | [enter date] | [enter date] | [Yes or N/A. If Yes, describe under "Reason for Change"] | [Enter new budget amount, if applicable] | [enter date] | [e.g., ESC]