## Project Tracking Sheet Example
Wind Facility - Operational Compliance Review
Task | Hrs Estimate | Hrs Actual | Assigned To | Due Date | Actual Date | Notes
Annual Report Review
Review OAR 345-026-0080(2) Criteria / Condition 122 | 8 | 6 | DK/TC | 2025-05-05 | 2025-05-05
Review Facility Modifications or Written Evaluations | 8 | 2 | DK | 2025-05-07 | 2025-05-07
Review Matrix and Attachments for the Following Conditions
Condition 3: Onsite manager contact information/quals | 1 | 1 | TC | 2025-06-23 | 2025-05-07
Condition 4: Site certificate violation reporting requirement | 1 | 1 | DK | 2025-05-08 | 2025-05-07
Condition 9: Financial assurance bond/letter of credit | 4 | 4 | DK/TC | 2025-05-08 | 2025-06-16
Condition 15: State and Local Permit approvals | 0.25 | 0.25 | TC | 2025-06-12
Condition 18: Equiptment parking | 0.5 | 1 | DK | 2025-05-08 | 2025-05-07
Condition 22: Landowner coordination on ag impacts during O&M | 2 | 1 | DK | 2025-05-13 | 2025-05-08
Condition 28: Turbine cover | 0.5 | 1 | DK | 2025-05-08 | 2025-05-07
Condition 29: Restoration of temporary impacts from O&M | 1 | 1 | DK | 2025-05-08 | 2025-05-07
Condition 30: Erosion inspection/results and maintenance activities | 4 | 2 | DK | 2025-05-13 | 2025-05-08
Condition 37: Incident reporting | 2 | 2 | DK | 2025-05-13 | 2025-06-17
Condition 39: Fencing and locked gates | 0.5 | 0.5 | DK | 2025-05-13 | 2025-05-08
Condition 41: No exterior turbine ladders and locked doors | 0.5 |  | TC
Condition 43: Ops safety monitoring program, and inspect blades on a regular basis | 8 |  | DK
Condition 44: SCADA system | 0.5 | 0.5 | DK | 2025-05-13 | 2025-05-08
Condition 47: Health and safety plan | 8 |  | DK | 2025-05-14
Condition 48: Turbine pad 10ft. Radius | 1 | 0.5 | DK | 2025-05-13 | 2025-05-08
Condition 49: Weed control plan | 20 |  | HA | 2025-05-13
Coordinate with HA for assessment of HMA, Reveg, and noxious weed monitoring |  |  | DK | 2025-05-13
Condition 52: Lighting | 20 | 0.25 | HA |  | 2025-06-16
Condition 61: WMMP / staff memo up date to Council | 20 |  | HA | 2025-05-12
Condition 62: Reveg | 20 | 0.25 | HA | 2025-05-13 | 2025-06-16
Coordinate with HA for assessment of HMA, Reveg, and noxious weed monitoring |  |  | DK
Condition 63: Habitat mitigation | 20 |  | HA | 2025-05-13
Coordinate with HA for assessment of HMA, Reveg, and noxious weed monitoring | 1 |  | DK | 2025-05-13
Condition 64: Provide Confederated Tribes of Warm Springs annual mitigation and monitoring reports | 1 | 0.25 | TC | 2025-05-15 | 2025-06-12
Condition 65: Annual CTWS Noxious weed consultation | 1 | 0.5 | TC | 2025-05-15 | 2025-06-16
Condition 75: Water use/onsite well usage | 1 |  | DK | 2025-05-15
Condition 76: Water for blade washing from offsite | 1 |  | DK | 2025-05-15
Condition 80: Hazerdous materials | 1 |  | TC
Condition 81: Spill incidents and reporting | 4 |  | DK | 2025-05-15
Condition 83: Discharge sanitary wastewater to an onsite septic system | 1 | 0.25 | TC | 2025-05-19 | 2025-06-12
Condition 87(a): Waste minimization | 1 |  | DK | 2025-05-19
Condition 87(b): Waste minimization | 1 |  | DK | 2025-05-19
Condition 87(c): Waste minimization | 1 |  | DK | 2025-05-19
Condition 87(d): Waste minimization | 1 |  | DK | 2025-05-19
Condition 88: Blade washing | 1 |  | DK | 2025-05-19
Condition 92: Maintain built-in fire prevention | 1 | 0.25 | TC | 2025-06-16
Condition 93: Fire management plan | 5 | 2 | TC | 2025-06-17
Condition 94: Vehicle fire equipment | 1 | 0.5 | DK | 2025-05-19
Condition 96: Provide all local fire departments names and phone of 24-hr staff | 2 | 1 | TC | 2025-06-23
Condition 97: Annual fire prevention and response training | 4 | 1 | TC | 2025-06-17
Condition 98: comply with fire protection recommendations | 1 | 0.5 | DK | 2025-06-17
Condition 99: EMF | 1 |  | TC
Condition 103: Operate as described in the site certificate | 1 |  | TC | 2025-05-21
Condtion 106: Mitigation required by standards | 1 |  | TC
Condition 107: OAR 345-027-0020(7): prevent any conditions for restoration | 1 |  | TC | 2025-05-21
Condition 108: Financial Assurance for Decommissioning | 1 | 0.25 | TC
Condition 115: Site certificate transfer requirements | 1 | 0.25 | TC | 2025-06-16
Condition 118: Transmission lines - NESC compliance and induced currents minimization | 1 | 1 | TC | 2025-06-17
Condition 120: General Monitoring | 1 |  | TC
Condition 122: Meet requirements of OAR 345-026-0080 |  |  | TC
Condition 124: Corespondence related to compliance | 2 |  | TC
Condition 125: Notification of Injury, hazard, or interference | 1 |  | DK | 2025-05-21
Condition 126: Northern Wormwood, Henderson's Ricegrass and other species | 2 |  | HA
Report review Completion Date | 182.25 | 32 |  | 2025-06-02
Inspection
Coordinate Field Maps/Survey123 map for site inspection with Bibi and Bailey | 2 |  | BB
Schedule inspection | 1 |  | BB
Conduct inspection | 21 |  | HA
Coordinate with Bailey to download inspections notes from ArcGIS | 2 |  | BB
Teams Meetings |  |  | TC
Coordinate with HA for their site inspection notes on HMA, reveg and noxious weeds | 4 |  | TC
Total Hours and inspection date | 30 | 0 |  | 2025-06-09
Operational Compliance Inspection Report
Draft Body of the Report | 10 |  | TC
Finalize the Report based on Annual Report Review and Inspection Findings | 17 |  | TC
Submit draft Report for Internal Review | 1 |  | TC
Issue Report, save documentation | 2 |  | TC
Complete Report Follow Up/Close Out Actions | 20 |  | TC
Inspection Report Completion Date | 50 | 0 | 0 | 2025-06-17
Total Hours | 262.25 | 32

## Compliance Matrix Example
2024 Annual Compliance Review
Legend
Applicable Observable O&M Condition = Certificate Holder Must Provide Narrative Explaining Compliance for the O&M Year. ODOE to Confirm in Site Inspection.
Applicable Evidence O&M Condition = Certificate Holder Must Report on Condition and Provide Evidence for Current and All Future Reporting Years. Compliance Sufficient.
Non-Compliant Applicable O&M Condition = Non-compliant in Previous Year or Follow Up Action Required - Report Substantively and Provide Evidence of Compliance with Condition
Not Applicable to Operation of the Facility = No Response Necessary.
Condition Number | Topic | Phase | Condition Language | Certificate Holder Annual Report - Compliance Summary and Demonstration (per April 2025 Annual Report) | ODOE Compliance Evaluation Per- April 2025 Annual Report
3 | Organizational Expertise | CON, OPS | During construction of the facility, the certificate holder shall have an on-site assistant construction manager who is qualified in environmental compliance to ensure compliance with all construction-related site certificate conditions. During operation, the certificate holder shall have a project manager who is qualified in environmental compliance to ensure compliance with all ongoing site certificate conditions. The certificate holder shall notify the Department of the name, telephone number, fax number and e-mail address of these managers and shall keep the Department informed of any change in this information.
4 | Organizational Expertise | GEN | Within 72 hours after discovery of conditions or circumstances that may violate the terms or conditions of the site certificate, the certificate holder shall report the conditions or circumstances to the Department.
9 | Retirement and Financial Insurance | OPS, RET | (b) The certificate holder shall annually adjust all bonds or letters of credit submitted in compliance with this condition to present value as of the date of issuance as described in (a)
9 | Retirement and Financial Insurance | OPS, RET | (c) The certificate holder shall use a form of bond or letter of credit approved by the Council.
9 | Retirement and Financial Insurance | OPS, RET | (d) The certificate holder shall use an issuer of the bond or letter of credit approved by the Council.
9 | Retirement and Financial Insurance | OPS, RET | (e) The certificate holder shall describe the status of all bonds or letters of credit for the facility in the annual report submitted to the Council under Condition (122).
9 | Retirement and Financial Insurance | OPS, RET | (f) The bond or letter of credit shall not be subject to revocation or reduction before retirement of the facility.
10 | Retirement and Financial Insurance | CON, OPS, RET | If the certificate holder elects to use a bond to meet the requirements of Condition (9), the certificate holder shall ensure that the surety is obligated to comply with the requirements of applicable statutes, Council rules and this site certificate when the surety exercises any legal or contractual right it may have to assume construction, operation or retirement of the facility. The certificate holder shall also ensure that the surety is obligated to notify the Council that it is exercising such rights and to obtain any Council approvals required by applicable statutes, Council rules and this site certificate before the surety commences any activity to complete construction, operate or retire the facility.
15 | Retirement and Financial Insurance | CON, OPS, RET | The certificate holder shall obtain all necessary state and local permits or approvals required for construction, operation and retirement of the facility or ensure that its contractors obtain necessary state and local permits or approvals.
18 | Land Use | GEN | The certificate holder shall ensure that no equipment or machinery is parked or stored on any county road except while in use.
22 | Land Use | OPS | During operation of the facility, the certificate holder, in cooperation with landowners, shall avoid impact on cultivated land to the extent reasonably possible when performing facility repair and maintenance activities.
28 | Soil Protection | CON, OPS | The certificate holder shall cover turbine pad areas with gravel or other non-erosive material immediately following exposure during construction and shall maintain the pad area covering during operation of the facility.
29 | Soil Protection | CON, OPS | During construction of the facility, the certificate holder shall restore areas that are temporarily disturbed in accordance with the methods, monitoring procedures and success criteria described in the Revegetation Plan that is incorporated in this order as Attachment B and as that Revegetation Plan may be amended from time to time. During operation of the facility, the certificate holder shall restore areas that are temporarily disturbed during facility maintenance or repairs according to the same methods and monitoring procedures.
30 | Soil Protection | OPS | During operation of the facility, the certificate holder shall routinely inspect and maintain all roads, pads and trenched areas and, as necessary, maintain or repair erosion control measures.
37 | Public Health and Safety Standards for Wind Energy Facilities | CON, OPS, RET | During construction, operation or retirement of the facility, the certificate holder shall notify the Department within 72 hours of any accidents that may result in public health and safety concerns, including mechanical failures on the site associated with construction or operation of the facility.
39 | Public Health and Safety Standards for Wind Energy Facilities | CON, OPS | The certificate holder shall enclose the facility substation with appropriate fencing and locked gates to protect the public from electrical hazards.
41 | Public Health and Safety Standards for Wind Energy Facilities | CON, OPS | The certificate holder shall construct turbine towers that are smooth steel structures with no exterior ladders or access to the turbine blades and shall install locked access doors accessible only to authorized personnel.
43 | Public Health and Safety Standards for Wind Energy Facilities | OPS | During operation of the facility, the certificate holder shall have an operational safety-monitoring program and shall inspect turbine blades on a regular basis for signs of wear. The certificate holder shall repair turbine blades as necessary to protect public safety.
44 | Public Health and Safety Standards for Wind Energy Facilities | OPS | During operation of the facility, the certificate holder shall install and maintain self-monitoring devices on each turbine, connected to a fault annunciation panel or supervisory control and data acquisition (SCADA) system at the O&M facility, to alert operators to potential dangerous conditions, and the certificate holder shall remedy any dangerous conditions immediately.
47 | Public Health and Safety Standards for Wind Energy Facilities | OPS | During operation of the facility, the certificate holder shall develop and implement a site health and safety plan that informs on-site employees and others what to do in case of an emergency and that includes the locations of fire extinguishers and nearby hospitals, important telephone numbers, and first aid techniques.
48 | Siting Standards for Wind Energy Facilities | CON, OPS | The certificate holder shall construct turbines on concrete foundations and shall cover the ground within a minimum 10-foot radius with non-flammable material. The certificate holder shall maintain the non-flammable pad area covering throughout operation of the facility.
49 | Siting Standards for Wind Energy Facilities | CON, OPS | During construction and operation of the facility, the certificate holder shall implement a plan to control the introduction and spread of noxious weeds. The certificate holder shall develop the weed control plan in consultation with the Sherman County Weed Control District and the Department.
52 | Siting Standards for Wind Energy Facilities | CON, OPS | The certificate holder shall not use exterior nighttime lighting except:
52 | Siting Standards for Wind Energy Facilities | CON, OPS | (a) The minimum turbine tower lighting required by the Federal Aviation Administration.
52 | Siting Standards for Wind Energy Facilities | CON, OPS | (b) Security lighting at the O&M buildings and substation, provided that such lighting is shielded or directed downward to reduce glare.
52 | Siting Standards for Wind Energy Facilities | CON, OPS | (c) Minimum lighting necessary for repairs or emergencies.
52 | Siting Standards for Wind Energy Facilities | CON | (d) Minimum lighting necessary for nighttime construction. The certificate holder may use lighting only at the work location and only directed downward to illuminate the work area at the turbine base or upward from the base to illuminate the turbine tower; construction lighting shall not be directed outward. The certificate holder shall use nighttime lighting only with the approval of the owner of the property on which the work is conducted and shall provide notice of nighttime construction to occupants of all residences within one-half mile of the construction site.
61 | Fish and Wildlife Habitat | CON, OPS | The certificate holder shall conduct wildlife monitoring and mitigation in accordance with the Wildlife Monitoring and Mitigation Plan that is incorporated in the Final Order on Amendment #2 as Attachment A and as may be amended from time to time. [Amendment #2]
62 | Fish and Wildlife Habitat | CON, OPS | The certificate holder shall restore areas that are temporarily disturbed during construction in accordance with the methods, monitoring procedures and success criteria set forth in the Revegetation Plan that is incorporated in the Final Order on Amendment #2 as Attachment B and as may be amended from time to time. [Amendment #2]
63 | Fish and Wildlife Habitat | PRE, CON, OPS | Before beginning construction of the facility, the certificate holder shall acquire the legal right to create, maintain and protect a habitat mitigation area for the life of the facility by means of an outright purchase, conservation easement or similar conveyance and shall provide a copy of the documentation to the Department. Within the habitat mitigation area, the certificate holder shall improve the habitat quality in accordance with the Habitat Mitigation Plan that is incorporated in the Final Order on Amendment #3 as Attachment C and as may be amended from time to time. [Amendments #2 and #3]
64 | Fish and Wildlife Habitat | GEN, OPS | For the life of the project, the certificate holder shall provide to the appropriate staff of the Confederated Tribes of the Warm Springs Reservation of Oregon the same annual mitigation and monitoring reports it submits to the Department.
65 | Fish and Wildlife Habitat | GEN, OPS | For the life of the project, the certificate holder shall consult annually with the appropriate staff of the Confederated Tribes of the Warm Springs Reservation of Oregon to discuss noxious weed or other issues that may arise from the close proximity of the facility site and tribal lands. The certificate holder shall provide a summary of that consultation in the annual report it provides to the Department.
75 | Public Services | PRO, OPS | Before beginning operation of the facility, the certificate holder shall have in operation a well suitable for delivering water, not exceeding 5,000 gallons per day, for domestic use at the facility's O&M buildings and, provided the rate of extraction would not exceed 5,000 gallons per day, blade-washing activities. The certificate holder shall not change the source of water for the facility’s domestic use without prior Council approval. [Amendment #3]
76 | Public Services | OPS | During operation of the facility, the certificate holder and its contractors shall obtain all water required for blade-washing activities from off-site sources previously permitted for such uses or from the on-site well, provided such use of well water would not cause the rate of extraction to exceed 5,000 gallons in any one-day period.
80 | Waste Minimization | GEN | The certificate holder shall use hazardous materials in a manner that protects public health, safety and the environment and shall comply with applicable local, state and federal environmental laws and regulations.
81 | Waste Minimization | CON, OPS | If a spill or release of hazardous materials occurs during construction or operation of the facility, the certificate holder shall notify the Department within 72 hours and shall clean up the spill or release and dispose of any contaminated soil or other materials according to applicable regulations. The certificate holder shall ensure that spill kits containing items such as absorbent pads are located on equipment and storage facilities to respond to accidental spills and shall instruct employees handling hazardous materials in the proper handling, storage and cleanup of these materials.
83 | Waste Minimization | OPS | During operation of the facility, the certificate holder shall discharge sanitary wastewater generated at the O&M buildings to a licensed on-site septic system in compliance with county permit requirements. The certificate holder shall design the septic system with a capacity that is less than 2,500 gallons per day. [Amendment #3]
87 | Waste Minimization | OPS | During operation of the facility, the certificate holder shall implement a waste management plan that includes but is not limited to the following measures:
87 | Waste Minimization | OPS | (a) Training employees to minimize and recycle solid waste;
87 | Waste Minimization | OPS | (b) Recycling paper products, metals, glass and plastics;
87 | Waste Minimization | OPS | (c) Collecting non-recyclable waste for transport to a landfill by a licensed waste hauler; and
87 | Waste Minimization | OPS | (d) Segregating all hazardous wastes, such as used oil, oily rags and oil-absorbent materials, mercury-containing lights and lead-acid and nickel-cadmium batteries for disposal by a licensed firm specializing in the proper recycling or disposal of hazardous wastes.
88 | Waste Minimization | OPS | During operation of the facility, the certificate holder may engage in blade-washing activities but shall ensure that these activities do not cause runoff of wash water from the site or discharges to surface waters, storm sewers or dry wells. The certificate holder shall not use acids, bases or metal brighteners with the wash water. The certificate may use biodegradable, phosphate-free cleaners sparingly. [Amendment #2]
92 | Public Health and Safety | ORG | During operation of the facility, the certificate holder shall maintain built-in fire prevention measures in each turbine that would shut down the turbine automatically before mechanical problems create excess heat or sparks.
93 | Public Health and Safety | CON, OPS | During construction and operation of the facility, the certificate holder shall develop and implement fire management plans in consultation with local fire control authorities to minimize the risk of fire and to respond appropriately to any fires that occur on the facility site. In developing the fire management plans, the certificate holder should take into account the dry nature of the region and should address risks on a seasonal basis.
94 | Public Health and Safety | CON, OPS | During construction and operation of the facility, the certificate holder shall ensure that each on-site company vehicle contains a fire extinguisher, water spray can, shovel, emergency response procedures book, and two-way radio for immediate communication with the O&M facility.
96 | Public Health and Safety | OPS | Upon beginning operation of the facility, the certificate holder shall provide to all local fire departments maps of the facility site. During operation of the facility, the certificate holder shall provide to all local fire departments the names and telephone numbers of facility personnel available to respond on a 24-hour basis in case of an emergency on the facility site.
97 | Public Health and Safety | OPS | During operation of the facility, the certificate holder shall ensure that all on-site employees receive annual fire prevention and response training by qualified instructors or members of the local fire department and that all employees are instructed to keep vehicles on roads and off dry grassland, except when off-road operation is required for emergency purposes.
98 | Public Health and Safety | OPS | During operation of the facility, the certificate holder shall comply with the written fire protection recommendations of the Fire Chief of the applicable Rural Fire Protection District and shall promptly provide to the Department any correspondence from the Fire Chief regarding those recommendations. [Amendment #3]
99 | Public Health and Safety | GEN, OPS | The certificate holder shall take reasonable steps to reduce or manage exposure to electromagnetic fields (EMF), consistent with Council findings presented in the “Report of EMF Committee to the Energy Facility Siting Council,” March 30, 1993, and subsequent findings. Effective on the date of this site certificate, the certificate holder shall provide information to the public, upon request, about EMF levels associated with the energy facility and related transmission lines.
103 | Conditions Required by Council Rules | GEN | The certificate holder shall design, construct, operate and retire the facility (a) substantially as described in the site certificate; (b) in compliance with the requirements of ORS Chapter 469, applicable Council rules, and applicable state and local laws, rules and ordinances in effect at the time the site certificate is issued; and (c) In compliance with all applicable permit requirements of other state agencies.
106 | Conditions Required by Council Rules |  | If the Council requires mitigation based on an affirmative finding under any standards of Division 22 or Division 24 of OAR Chapter 345, the certificate holder shall consult with affected state agencies and local governments designated by the Council and shall develop specific mitigation plans consistent with Council findings under the relevant standards. The certificate holder must submit the mitigation plans to the Office and receive Office approval before beginning construction or, as appropriate, operation of the facility.
107 | Conditions Required by Council Rules | GEN | OAR 345-027-0020(7): The certificate holder shall prevent the development of any conditions on the site that would preclude restoration of the site to a useful, non-hazardous condition to the extent that prevention of such site conditions is within the control of the certificate holder.
108 | Conditions Required by Council Rules | PRE, CON, OPS, RET | OAR 345-027-0020(8): Before beginning construction of the facility, the certificate holder shall submit to the State of Oregon, through the Council, a bond or letter of credit in a form and amount satisfactory to the Council to restore the site to a useful, non-hazardous condition. The certificate holder shall maintain a bond or letter of credit in effect at all times until the facility has been retired. The Council may specify different amounts for the bond or letter of credit during construction and during operation of the facility. [Amendment #3]
115 | Conditions Required by Council Rules | GEN, OPS | OAR 345-027-0020(15): Before any transfer of ownership of the facility or ownership of the site certificate holder, the certificate holder shall inform the Department of the proposed new owners. The requirements of OAR 345-027-0100 apply to any transfer of ownership that requires a transfer of the site certificate. [Amendment #3]
118 | Conditions Required by Council Rules | PRE, CON, OPS | OAR 345-027-0023(4): If the facility includes any transmission line under Council jurisdiction:
118 | Conditions Required by Council Rules | PRE, CON, OPS | a) The certificate holder shall design, construct and operate the transmission line in accordance with the requirements of the National Electrical Safety Code (American National Standards Institute, Section C2, 1997 Edition); and
118 | Conditions Required by Council Rules | PRE, CON, OPS | (b) The certificate holder shall develop and implement a program that provides reasonable assurance that all fences, gates, cattle guards, trailers, or other objects or structures of a permanent nature that could become inadvertently charged with electricity are grounded or bonded throughout the life of the line.
120 | Conditions Required by Council Rules | GEN | OAR 345-027-0028: The following general monitoring conditions apply:
120 | Conditions Required by Council Rules | GEN | (a) The certificate holder shall consult with affected state agencies, local governments and tribes and shall develop specific monitoring programs for impacts to resources protected by the standards of Divisions 22 and 24 of OAR Chapter 345 and resources addressed by applicable statutes, administrative rules and local ordinances. The certificate holder must submit the monitoring programs to the Department of Energy and receive Department approval before beginning construction or, as appropriate, operation of the facility.
120 | Conditions Required by Council Rules | GEN | (b) The certificate holder shall implement the approved monitoring programs described in section (a) and monitoring programs required by permitting agencies and local governments.
120 | Conditions Required by Council Rules | GEN | (c) For each monitoring program described in sections (a) and (b), the certificate holder shall have quality assurance measures approved by the Department before beginning construction or, as appropriate, before beginning commercial operation.
120 | Conditions Required by Council Rules | GEN | (d) If the certificate holder becomes aware of a significant environmental change or impact attributable to the facility, the certificate holder shall, as soon as possible, submit a written report to the Department describing the impact on the facility and any affected site certificate conditions.
122 | Conditions Required by Council Rules | GEN | OAR 345-026-0080: The certificate holder shall report according to the following requirements:
122 | Conditions Required by Council Rules | CON, OPS | (a) General reporting obligation for energy facilities under construction or operating:
122 | Conditions Required by Council Rules | CON | (i) Within six months after beginning construction, and every six months thereafter during construction of the energy facility and related or supporting facilities, the certificate holder shall submit a semiannual construction progress report to the Department of Energy. In each construction progress report, the certificate holder shall describe any significant changes to major milestones for construction. The certificate holder shall include such information related to construction as specified in the site certificate. When the reporting date coincides, the certificate holder may include the construction progress report within the annual report described in this Condition.
122 | Conditions Required by Council Rules | CON, OPS | (ii) By April 30 of each year after beginning construction, the certificate holder shall submit an annual report to the Department addressing the subjects listed in this Condition. The Council Secretary and the certificate holder may, by mutual agreement, change the reporting date.
122 | Conditions Required by Council Rules | CON, OPS | (iii) To the extent that information required by this rule is contained in reports the certificate holder submits to other state, federal or local agencies, the certificate holder may submit excerpts from such other reports to satisfy this rule. The Council reserves the right to request full copies of such excerpted reports.
122 | Conditions Required by Council Rules | OPS | (b) In the annual report, the certificate holder shall include the following information for the calendar year preceding the date of the report:
122 | Conditions Required by Council Rules | OPS | (i) Facility Status: An overview of site conditions, the status of facilities under construction, and a summary of the operating experience of facilities that are in operation. In this section of the annual report, the certificate holder shall describe any unusual events, such as earthquakes, extraordinary windstorms, major accidents or the like that occurred during the year and that had a significant adverse impact on the facility.
122 | Conditions Required by Council Rules | OPS | (ii) Reliability and Efficiency of Power Production: For electric power plants, the plant availability and capacity factors for the reporting year. The certificate holder shall describe any equipment failures or plant breakdowns that had a significant impact on those factors and shall describe any actions taken to prevent recurrence of such problems;
122 | Conditions Required by Council Rules | OPS | (iii) Fuel Use: For thermal power plants:
122 | Conditions Required by Council Rules | OPS | (A) The efficiency with which the power plant converts fuel into electric energy. If the fuel chargeable to power heat rate was evaluated when the facility was sited, the certificate holder shall calculate efficiency using the same formula and assumptions, but using actual data; and
122 | Conditions Required by Council Rules | OPS | (B) The facility's annual hours of operation by fuel type and, every five years after beginning operation, a summary of the annual hours of operation by fuel type as described in OAR 345-024-0590(5).
122 | Conditions Required by Council Rules | OPS | (iv) Status of Surety Information: Documentation demonstrating that bonds or letters of credit as described in the site certificate are in full force and effect and will remain in full force and effect for the term of the next reporting period;
122 | Conditions Required by Council Rules | OPS | (v) Monitoring Report: A list and description of all significant monitoring and mitigation activities performed during the previous year in accordance with site certificate terms and conditions, a summary of the results of those activities, and a discussion of any significant changes to any monitoring or mitigation program, including the reason for any such changes.
122 | Conditions Required by Council Rules | OPS | (vi) Compliance Report: A description of all instances of noncompliance with a site certificate condition. For ease of review, the certificate holder shall, in this section of the report, use numbered subparagraphs corresponding to the applicable sections of the site certificate.
122 | Conditions Required by Council Rules | OPS | (vii) Facility Modification Report: A summary of changes to the facility that the certificate holder has determined do not require a site certificate amendment in accordance with OAR 345-027-0050.
124 | Conditions Required by Council Rules | GEN | OAR 345-026-0105: The certificate holder and the Department of Energy shall exchange copies of all correspondence or summaries of correspondence related to compliance with statutes, rules and local ordinances on which the Council determined compliance, except for material withheld from public disclosure under state or federal law or under Council rules. The certificate holder may submit abstracts of reports in place of full reports; however, the certificate holder shall provide full copies of abstracted reports and any summarized correspondence at the request of the Department. [Amendment #3]
125 | Conditions Required by Council Rules | GEN, OPS | OAR 345-026-0170: The certificate holder shall notify the Department of Energy within 72 hours of any occurrence involving the facility if:
125 | Conditions Required by Council Rules | GEN, OPS | (a) There is an attempt by anyone to interfere with its safe operation;
125 | Conditions Required by Council Rules | GEN, OPS | (b) A natural event such as an earthquake, flood, tsunami or tornado, or a human-caused event such as a fire or explosion affects or threatens to affect the public health and safety or the environment; or
125 | Conditions Required by Council Rules | GEN, OPS | (c) There is any fatal injury at the facility.
126 | Conditions Relating to Amendment 2 | CON, OPS | Prior to any disturbance in the areas of the site added in the Final Order for Amendment #2, the certificate holder shall deliver to the Department the results of a spring survey of Crossing G, conducted during the appropriate bloom time for Northern wormwood and Henderson’s ricegrass. If Northern wormwood or any other protected rare plant species are observed during the spring survey, the certificate holder shall ensure that construction and operation of the facility will have no impact on the rare plant habitat. [Amendment #2]