# Tailored Rollout Approaches with Policy Development and School Board Approval

Below are two implementation plans to help districts launch a personal electronic device (PED) policy aligned with EO 25-09. Each plan outlines steps for developing a local policy, presenting it to the school board, and ensuring consistent implementation across schools. Districts can adapt the plans to fit their specific needs and priorities. All policies must be adopted by October 31, 2025, and fully implemented by January 1, 2026, as required by the Executive Order.

# Plan 1. Policy in Place. Needs Revisions to Align with EO 25-09

Best For: Districts with existing PED policy that needs slight revisions to be ready to launch before the school year begins.

Timeline:

Late Summer/Early Fall= policy revision, board approval, and planning

Start of School = full implementation

### Key Actions:

Late Summer:

- Review current PED policy to ensure alignment with EO 25-09:

  - Define “bell to bell” as from the beginning of the school day to end of the school day

  - Add exemption language

  - Integrate restorative, non-punitive enforcement language

- Convene a small workgroup of educators, students, and family representatives to provide feedback on the revised draft

- Prepare plain-language and translated summaries of the revised policy

Late Summer/Early Fall:

- Present the updated policy to the school board for review and approval

  - Provide board members with an FAQ, sample parent communications, and summary of community input

  - Emphasize how updates align with district goals and state law

- Finalize board-approved policy for public distribution

- Train all staff on:

  - Revised policy and scope

  - Exemption process for IEP/504 and health plans

  - Restorative response protocols

- Prepare policy roll-out materials for classrooms, families, and common spaces

- Teach policy to students in classroom meetings or advisory

- Share translated policy letters and FAQs with families

- Begin enforcement with Tiered Restorative Response

- Monitor early trends and provide coaching as needed

# Plan 2: Teaching into the Policy. Full Implementation in Late Fall/Winter

Best For: Schools or districts that need time to build community understanding, staff capacity, and co-create the policy before implementation.

Timeline:

Late Summer/Early Fall = policy development, partner engagement

Fall/Early Winter = board approval and phased rollout

January onward = full implementation

### Key Actions:

Late Summer/Early Fall:

- Facilitate learning sessions with staff, students, and families on:

  - Digital distraction and executive functioning

  - The goals and requirements of EO 25-09

  - Trauma-informed and restorative school discipline

- Co-design a draft PED policy with community input

  - Pilot draft practices in a few classrooms or grade levels

  - Collect real-time feedback to refine the policy

Fall:

- Present the refined policy to the school board for adoption

  - Include student data and testimonials

  - Offer an implementation timeline and impact plan

- Develop translated, family-friendly communications and emergency contact protocols

Early Winter:

- Pre-launch “teaching phase” in classrooms:

  - Use reflection activities, student-designed posters, and wellness challenges

  - Offer restorative circles for early violations or concerns

- Begin phased enforcement:

  - Week 1: Teach and reteach expectations

  - Week 2: Begin using restorative reflection forms

  - Week 3+: Formal enforcement with support structures

January:

- Full policy enforcement begins with implementation, monitoring, exemption, and enforcement processes active

- Regular check-ins with implementation teams and data reviews

## Additional Resources to Support Plan Development and Adoption

### School Board Briefing Tips (For All Plans)

When presenting the PED policy to your board:

- Provide a 1-page summary of EO 25-09 and what it requires

- Share evidence from student focus groups and educator interviews

- Emphasize restorative strategies

- Offer a clear timeline and highlight staff, student, and family engagement

- Prepare for common concerns (emergency contact, discipline, enforcement consistency)

### Implementation Timeline Planning Grid

Purpose: To help districts plan out clear phases of policy rollout and support.

| Phase | Key Actions | Responsible Person/Team | Partners Involved | Timeline | Notes |
| --- | --- | --- | --- | --- | --- |
| Pre-Launch |  |  |  |  |  |
| Launch Week |  |  |  |  |  |
| First 30 Days |  |  |  |  |  |
| Troubleshooting & Midpoint Review |  |  |  |  |  |