# Project Implementation Timeline

This example timeline illustrates how a district might roll out the CTE Safety System across multiple programs, ensuring each receives focused attention and support. For smaller schools with fewer programs, a condensed approach is provided below.

## Example for Larger Districts

In this example, the timeline is strategically developed to allow five (5) dedicated days for each program, ensuring a thorough and efficient rollout while accommodating potential scheduling adjustments. Dates are for illustrative purposes only.

### Key Steps in the Timeline Development

Kick-Off and Initial Preparation

- August 1: Kick-off meeting with teachers, administrators, and the Safety and Risk Management Services (SRMS) team to review the plan, establish expectations, and set goals.

- August 2: Teachers receive the Safety System Kit, containing the tools and resources needed to begin implementation.

Program-Specific Implementation Phases

Each program is allotted a 5-day period dedicated to safety system implementation, ensuring thorough attention and the flexibility to adapt schedules as needed. In the sample timeline provided, each career area has a full week to implement the safety system. This division ensures ample support for every program area. However, it does necessitate a substantial time investment for the SRMS.

Example Timeline for Programs

- Diesel Program: August 2–6

- Automotive Program: August 7–11

- Engineering Program: August 12–16

- Culinary Program: August 17–22

- Agriculture Program: August 23–29

- Woodshop Program: August 30 – September 3

Finalization and Review

- The timeline concludes with a final review phase to address any outstanding tasks, resolve issues identified during implementation, and prepare for full operational safety compliance.

By allotting five days per program, this timeline ensures a comprehensive and manageable process that supports the successful adoption of the CTE Safety System across multiple areas.

## Example for Smaller Schools

For smaller schools with only one or two CTE programs, the implementation timeline can be condensed to reflect their specific needs.

### Key Steps in the Timeline Development

Kick-Off and Initial Preparation

- Day 1: Hold a kick-off meeting with the program instructor(s) and administrators to review the implementation plan and distribute the Safety System Kit.

Program Implementation Phase

- Days 2–4: Dedicate three days to implementing the safety system in the program(s). Focus on:

  - Conducting equipment inventories and hazard assessments.

  - Training staff and students on safety protocols.

  - Setting up safety signage and other physical safety measures.

Finalization and Review

- Day 5: Review progress, address any gaps, and finalize the safety plan to ensure the program is ready for full operational compliance.

Example Timeline for One Program

- Woodworking Program: August 1–5

For schools with two programs, you can repeat the steps over two consecutive weeks, adjusting as necessary to accommodate smaller team sizes and resources.

### Considerations for Limited Resources

Some districts may not have the financial resources to bring teachers in during off-contract time for the implementation process. In such cases, finding time within the regular school day becomes essential. Schools can utilize existing curriculum or team collaboration times built into their schedules to prioritize safety planning. Using this time to focus on the CTE Safety System is critical, as it provides teachers the opportunity to address safety measures effectively without requiring additional funding or disrupting other instructional responsibilities.