## instructions
This workbook is to be used in developing a workplan for recommendations associated with the low-bid contracting barrier identified by the DBE Committee. The Committee developed two recommendations related to this barrier:
1. Create more contracting processes that waive the lowest bid requirements, maybe other criteria, including best value or “lowest and best” to provide for contracting flexibility needed to allow DBE firms to compete.
2. Modify the mentor-protégé program for the partnership to center on small firms winning more work after competing.
STEPS to complete workplan
1. Review recommendations and barrier paper.
2. Review information on recommendation 1 tab, row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
3. Review information on recommendation 2 tab row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
4. In step 1, include names, contact information, and roles for ODOT team members who are key to advancing each recommendation.
5. In step 2, provide clear descriptions of each milestone, including what decision will be made at each milestone, who will make that decision, and the outcome of that decision. Add activities necessary to complete each action to complete the recommendation.
6. In step 3, include any collaborators in the partners column.
7. In step 4, provide realistic timelines for completion of each activity and action.
8. In column 1, add actions that will be necessary to complete the recommendations, including activities for each.
9. As you add actions, include those in your barriers and recommendations change log.
10. Repeat steps 4 through 9 for recommendation 2.
11. Fill out additional information as your clarify you process.

## recommendation 1
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 5: Low-bid contracting, Recommendation 1 Create more contracting processes that waive the lowest bid requirements, maybe other criteria, including best value or “lowest and best” to provide for contracting flexibility needed to allow DBE firms to compete.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Work with relevant ODOT departments to develop a plan for defining a best value approach to bid evaluation. | Kevin Cassidy - SME - OPO Holli Pick - SME - Alternative Delivery Diponker Mukherjee - SME - DBE Jamie Viramontes - SME - Project Delivery Greg Stellmach- Advisory - Contract Admin Office of Maintenance Rep - SME - Operations OSECR Business Navigator - SME - Small Business | *Develop a survey for certified firms that bid with ODOT to better define low bid barriers so we can effectively address barriers toward better outcomes *Explore opportunities within ORS 279B to utilize best value procurement - post a sample bid document and how to complete it *Review Port of Portland and City of Portland programs for best practices *Work with ADS and FHWA to develop DBE/Small Contracting requirements to use in RFP process to identify and utilize small business firms (work underway) | Potential partners: * Federal Highway Administration (FHWA) and other federal bodies * Oregon Transportation Commission (OTC) * Other relevant ODOT departments *COBID - Carrie Braxandall *Business Oregon - Feather Sams-Huesties | *Develop a survey for certified firms that bid with ODOT to better define low bid barriers so we can effectively address barriers toward better outcomes (Fall 2023) *Explore opportunities within ORS 279B to utilize best value procurement (By Dec 2023) *Review Port of Portland and City of Portland programs for best practices. (By Dec 2023) *Work with ADS and FHWA to develop DBE/Small Contracting requirements to use in RFP process to identify and utilize small business firms (work underway)
| Action 2: Promote the new law regarding primes using certified firms to win points but then not using the certified firm on the project or for a smaller scope of work than agreed to. | Diponker Mukherjee - SME - DBE Jamie Viramontes - SME - Project Delivery Greg Stellmach- Advisory - Contract Admin Office of Maintenance Rep - SME - Operations OSECR Business Navigator - SME - Small Business OPO - Marie/Kevin/Joni | *Work with Advisory Committee to obtain more information on the recommendation such as is this new law federal or state, an oregon law or from another state? *Research law *Determine applicability for ODOT use *Write rules, specifications, contract verbiage as needed for implementation *Develop implementation and communication plans | *DOJ *The agency that passed this law *Any state agencies that are implementing this law | *Work with Advisory Committee to obtain more information on the recommendation such as is this new law federal or state, an oregon law or from another state? (Spring 2024) *Research law (Dependent on Advisory Committee Outcomes) *Determine applicability for ODOT use *Write rules, specifications, contract verbiage as needed for implementation *Develop implementation and communication plans
| Action 3: Redefine the rules around which contracts are set as low bid, including working with the legislature, OTC, and others. | Diponker Mukherjee - SME - DBE Holli Pick - SME - Alternative Delivery Jamie Viramontes - Advisory - Project Delivery Marie/Kevin/Joni - SME - Procurement OSECR Business Navigator - SME - Small Business | *Persue a goal program that utilizes State funding *Develop rules, specifications, contract language as needed *Work with OECR to determine status of Small Contracting Program and Maintenance Emergency Services list, do these programs address some of these barriers? *Look at expanding ESB Certification beyond 5 years. *Look at smaller units of work to break out. *Educate DBE community about ESB Program, Small Contracting Program, Maintenance Emergency Services List *Work with ADS and bundling subcommittee to identify projects which will accomodate non low bid contracting methods. | Potential partners: *DOJ *Oregon Transportation Commission | *Persue a goal program that utilizes State funding (Fall 2023) *Develop rules, specifications, contract language as needed (Spring 2024) *Work with OECR to determine status of Small Contracting Program and Maintenance Emergency Services list, do these programs address some of these barriers? Look at expanding ESB Certification beyond 5 years. Look at smaller units of work to brake out. (Fall 2023) *Educate DBE community about ESB Program, Small Contracting Program, Maintenance Emergency Services List (ongoing) *Work with ADS and bundling subcommittee to identify projects which will accomodate non low bid contracting methods. (Spring 2024)
[Action 4]
[Action 5]
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 2
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 5: Low-bid contracts, Recommendation 2 Modify the mentor-protégé program for the partnership to center on small firms winning more work after competing.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Explore options to incentive large firms that participate in the mentor-protégé program to invest in their protégé firms. | Kevin Cassidy/ Kayleen Warner - OPO Diponker Mukherjee - OECR Greg Stellmach or other resource from CAU Jaime Viramontes - PCO | *Discussion with Diponker and work group regarding current mentor protégé partnership with the Port of Portland *Presentation by POP re: their program *Research other state programs *Partner with support services providers that offer similar information that would be learned from a mentor *Include this information and these providers on new resource webpage. | Port of Portland Supportive Services Providers Association of General Contractors | *Discussion with Diponker and work group regarding current mentor protégé partnership with the Port of Portland (Summer 2023) *Presentation by POP re: their program (Fall 2023) *Research other state programs (Fall 2023) *Partner with support services providers that offer similar information that would be learned from a mentor (Spring 2024) *Include this information and these providers on new resource webpage. (Spring 2024)
| Action 2: Look at capacity building programs like the programs at WSDOT and the Port of Portland. | Kevin Cassidy/ Kayleen Warner - OPO Diponker Mukherjee - OECR Greg Stellmach or other resource from CAU Jaime Viramontes - PCO Zac Cartwright - OPO Risk and Insurance | *Reserch capacity building programs at WSDOT and Port of Portland *Evaluate programs for ODOT use. *Implement and communicate programs *Develop and post a sample bid document and how to complete it. *Work with OECR to develop, advertise, and deliver a class for small busninesses on bonding and insurance. | Washington State Department of Transportation (WSDOT) Port of Seattle | *Reserch capacity building programs at WSDOT and Port of Portland (Fall 2023) *Evaluate programs for ODOT use. (Winter 2024) *Implement and communicate programs (Spring 2024) *Develop and post a sample bid document and how to complete it. (Fall 2023) *Work with OECR to develop, advertise, and deliver a class for small busninesses on bonding and insurance. (Spring 2024)
[Action 3]
[Action 4]
[Action 5]
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan