## Sheet1
PE-CE OUTSOURCED REPORT
AS OF: June 25 2026
FOR REGION(S): Region 2
FOR ADMIN ID(S): ODOT, ODOT/LOCAL
Report Contact:PMO
FOR COUNTY(S): ALL
FOR KEY NUMBER(S): ALL
FOR DBE GOAL: All
STIP-FP Data |  | MSP Data | [8 empty] | Programmed STIP-FP Data | [5 empty] | Calculation | MSP Data |  | CRCT
Key # |  | Project Name |  |  | PCS Region | ODOT Lead | Outsourced PE | PE Outsourced Discipline | Outsourced CE | CE Outsourced Discipline | Project Description | Admin By | County | Work Type | PE/PL Programmed Budget | Total Programmed Project Budget | Anticipated RFP Release Time | Kick-off Meeting Date | Bid Let Date | Anticipated DBE Goal
22656 |  | Luckiamute River, Helmick Road bridge (Polk Co) |  |  | Region 2 | GREENWAY VALERIE | F/S |  | F/S |  | Rehabilitation of bridge including a phase 1 seismic retrofit, erosion control repair, and other general maintenance needs to preserve the historic integrity of the bridge. | ODOT/LOCAL | POLK | BRIDGE | 698300 | 3828500 |  | 2026-12-14 17:00 | 2029-08-24 17:00 | TBD: 0 – 22%
22709 |  | Northwest Oregon pedestrian crossing enhancements (2027) |  |  | Region 2 | JACOBSON AJ | No |  | CA/CEI |  | Complete design to increase pedestrian safety at several state highway intersections in the NW part of the state. Construction will be completed where funding allows. Enhancements will include a mix of signs with flashing lights, intersection lighting and median islands and upgrading to ADA compliant curbs. | ODOT | LINCOLN | SAFETY | 814477 | 2959010 |  | 2023-12-05 17:00 | 2026-10-08 17:00 | TBD: 0 – 22%
23457 |  | OR99W Corridor Safety & Intersection Improvements |  |  | Region 2 | NELSON SCOTT | No |  | F/S |  | Design and construct improvements to intersections throughout the OR99W corridor with various safety features including turn lanes and improved/enhanced signing to improve driver and pedestrian safety. Complete (to DAP) design of a roundabout at OR-99W and OR18 and purchase the associated right of way. | ODOT | YAMHILL | SAFETY | 2000000 | 8457817.9 |  | 2024-03-05 17:00 | 2026-10-01 17:00 | 0.00%
Report Total: 3

## Sheet2
About this report Report name: PE-CE Outsourced Report Purpose: To provide forecasted outsourced work to industry partners. This report is posted to the external ODOT Procurement website weekly. Definitions and filters: Anticipated DBE goal shows the range of possible DBE goal percentages if the goal has not yet been entered in the source system. Filter(s): Projects show on this report according to the following: PE & CE or just PE outsourced: Project will be on the report for 12 months before the PDT kick off date until 3 months after the PDT kick off date. Or until the project has gone to bid through OregonBuys. Just CE outsourced: Project will be on the report for 9 months before the bid let date until 1 month after the bid let date. Or until the project has gone to bid through OregonBuys. Anticipated RFP Release Time calculation: PE & CE or just PE Outsourced: PDT Kick off - 140 days Just CE outsourced: PS&E Submittal date - 180 days Data sources: RMS, STIP, CivilRights