## Sheet1
PE-CE OUTSOURCED REPORT
AS OF: June 25 2026
FOR REGION(S): Region 3
FOR ADMIN ID(S): ODOT, ODOT/LOCAL
Report Contact:PMO
FOR COUNTY(S): ALL
FOR KEY NUMBER(S): ALL
FOR DBE GOAL: All
STIP-FP Data |  | MSP Data | [8 empty] | Programmed STIP-FP Data | [5 empty] | Calculation | MSP Data |  | CRCT
Key # |  | Project Name |  |  | PCS Region | ODOT Lead | Outsourced PE | PE Outsourced Discipline | Outsourced CE | CE Outsourced Discipline | Project Description | Admin By | County | Work Type | PE/PL Programmed Budget | Total Programmed Project Budget | Anticipated RFP Release Time | Kick-off Meeting Date | Bid Let Date | Anticipated DBE Goal
22562 |  | I-5: Smith and Sexton Pass |  |  | Region 3 | BENTEA STEPHANIE L | 40% | Environmental, Traffic ITS | No |  | Installation of a curve warning sign and message sign to provide additional safety and real-time communication with the travelling public. | ODOT | JOSEPHINE | OP-ITS | 300000 | 300000 |  | 2026-08-05 17:00 | 2029-02-08 17:00 | TBD: 0 – 22%
22641 |  | I-5: Cabin Creek - Sutherlin |  |  | Region 3 | BENTEA STEPHANIE L | 20% | Pavements | No |  | Design activities through Design Acceptance Phase for future repair of the pavement to reduce costly and repetitive maintenance and provide a safer traveling experience for the public. | ODOT | DOUGLAS | PRESRV | 750000 | 750000 |  | 2026-08-10 17:00 |  | TBD: 0 – 22%
23063 |  | Jackson County curb ramps phase 4 |  |  | Region 3 | THOM ROGER | No |  | CA/CEI |  | Design curb ramps along various segments of OR62 at MP 9.42 and 10.09, OR66 at MP's 0.88, 0.95, 1.04, 1.18, 1.28, 1.38, 1.43, 1.53, 1.72, 1.77 and 1.83, OR99 at MPs 13.82, 14.07, 14.20, 14.59, 17.95 and 18.87 to meet compliance with the Americans with Disabilities Act (ADA) standards. | ODOT | JACKSON | ADAP | 1500000 | 6075000 |  | 2025-02-13 17:00 | 2026-12-17 17:00 | TBD: 0 – 22%
23873 |  | Electric Vehicle Charging Project (Brookings) |  |  | Region 3 | DEWALD TERESA L | F/S |  | F/S |  | Install two level 2 charging stations at Bookings City Hall for city use only, two make ready ports, and two electric light-duty trucks. | ODOT | CURRY | OP-CARBON | 90000 | 490000 |  | 2026-08-26 17:00 | 2027-11-02 17:00 | TBD: 0 – 22%
Report Total: 4

## Sheet2
About this report Report name: PE-CE Outsourced Report Purpose: To provide forecasted outsourced work to industry partners. This report is posted to the external ODOT Procurement website weekly. Definitions and filters: Anticipated DBE goal shows the range of possible DBE goal percentages if the goal has not yet been entered in the source system. Filter(s): Projects show on this report according to the following: PE & CE or just PE outsourced: Project will be on the report for 12 months before the PDT kick off date until 3 months after the PDT kick off date. Or until the project has gone to bid through OregonBuys. Just CE outsourced: Project will be on the report for 9 months before the bid let date until 1 month after the bid let date. Or until the project has gone to bid through OregonBuys. Anticipated RFP Release Time calculation: PE & CE or just PE Outsourced: PDT Kick off - 140 days Just CE outsourced: PS&E Submittal date - 180 days Data sources: RMS, STIP, CivilRights