## Project Risk Register
| Project Risk Register | [7 empty] | Results ↓ |  | ↓ Cost Risk ↓ |  | ↓ Schedule Risk ↓ |  | ↓ Risk Totals ↓
|  |  | K# : | [7 empty] | PL | 0 | PL | 0
|  |  | Project Name: | [7 empty] | PE | 0 | PE | 0 | Total Cost Risk |  | 0
|  |  | TPM/RE-CP: | [7 empty] | CN | 0 | CN | 0 |  | Total Schedule Risk | 0
|  |  | Area Manager: | [7 empty] | RW | 0 | RW | 0 | Design Schedule Risk |  | 0
[11 empty] | UR | 0 | UR | 0 | Bid Date Variability
|  |  | Last Review Date: | [7 empty] | OT | 0 | OT | 0
| Risk Identification | [7 empty] | Cost Impact - In Thousands |  |  |  |  | Schedule Impact - In Months |  |  |  | Risk Response Plan |  |  |  |  | Pre-Response |  |  | Post-Response |  |  |  |  | Monitor and Review
Key No. | Risk No. | Date Id. | Risk Title | Phase | Critical Path? | Nature | Detailed Description of Risk Event | Status | Probability | Min $ | Most Likely $ | Max $ | Expected Value $ | Min 6 | Most Likely 6 | Max 6 | Expected Value 6 | $ Risk Rank | 6 Risk Rank | Strategy | Risk Owner | Response action(s) to be taken | Min (P10) | ML (P50) | Max (P90) | Min (P10) | ML (P50) | Max (P90) | Threat | Opportunity | Date, Status, and Review Comments | Date Updated
| 1 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 2 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 3 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 4 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 5 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 6 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 7 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 8 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 9 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 10 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 11 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 12 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 13 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 14 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 15 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 16 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 17 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 18 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 19 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 20 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 21 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 22 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 23 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 24 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 25 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 26 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 27 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 28 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 29 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 30 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 31 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 32 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 33 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 34 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 35 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 36 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 37 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 38 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 39 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 40 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 41 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 42 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 43 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 44 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 45 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 46 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 47 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 48 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 49 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 50 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 51 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 52 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 53 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 54 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 55 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 56 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 57 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 58 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 59 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 60 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 61 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 62 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 63 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 64 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 65 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 66 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 67 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 68 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 69 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 70 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 71 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 72 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 73 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 74 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 75 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 76 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 77 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 78 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 79 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 80 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 81 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 82 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 83 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 84 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 85 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 86 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 87 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 88 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 89 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 90 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 91 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 92 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 93 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 94 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 95 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 96 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 97 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 98 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 99 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 100 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 101 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 102 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 103 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 104 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 105 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 106 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 107 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 108 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 109 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 110 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 111 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 112 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 113 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 114 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 115 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 116 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 117 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 118 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 119 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 120 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 121 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 122 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 123 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 124 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 125 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 126 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 127 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 128 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 129 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 130 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 131 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 132 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 133 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 134 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 135 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 136 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 137 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 138 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 139 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 140 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 141 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 142 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 143 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 144 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 145 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 146 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 147 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 148 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 149 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
| 150 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
Guidance:
Proper use of this tool assumes familiarity with Project Risk Management concepts. A guide has been developed to assist users in managing project risks:
https://www.oregon.gov/odot/Engineering/Pages/VE-RM.aspx
https://www.oregon.gov/odot/Engineering/Docs_RMVE/Managing-Project-Risks-ODOT-STIP.pdf
https://www.oregon.gov/odot/Engineering/Docs_RMVE/VE-Team-Member-Guide.pdf

## Example - Project Risk Register
| Project Risk Register | [7 empty] | Results ↓ |  | ↓ Cost Risk ↓ |  | ↓ Schedule Risk ↓ |  | ↓ Risk Totals ↓
|  |  | K# : | K1234 | [6 empty] | PL | 0 | PL | 0
|  |  | Project Name: | Example | [6 empty] | PE | 100566.6667 | PE | 1.8 | Total Cost Risk |  | 851350
|  |  | TPM/RE-CP: | [7 empty] | CN | 750783.3333 | CN | 0.3 |  | Total Schedule Risk | 2.1
|  |  | Area Manager: | [7 empty] | RW | 0 | RW | 0 | Design Schedule Risk |  | 1.8
[11 empty] | UR | 0 | UR | 0 | Bid Date Variability |  | Yellow
|  |  | Last Review Date: | [7 empty] | OT | 0 | OT | 0
| Risk Identification | [7 empty] | Cost Impact - In Thousands |  |  |  |  | Schedule Impact - In Months |  |  |  | Risk Response Plan |  |  |  |  | Pre-Response |  |  | Post-Response |  |  |  |  | Monitor and Review
Key No. | Risk No. | Date Id. | Risk Title | Phase | Critical Path? | Nature | Detailed Description of Risk Event | Status | Probability | Min $ | Most Likely $ | Max $ | Expected Value $ | Min 6 | Most Likely 6 | Max 6 | Expected Value 6 | $ Risk Rank | 6 Risk Rank | Strategy | Risk Owner | Response action(s) to be taken | Min (P10) | ML (P50) | Max (P90) | Min (P10) | ML (P50) | Max (P90) | Threat | Opportunity | Date, Status, and Review Comments | Date Updated
K1234 | 1 | 2021-06-01 | Design Acceptance Approval | PE | yes | Threat | The project assumes design exception approval for substandard super-elevation of 13% and a substandard spiral length of 200' for the Exit 400 SB off ramp. If the design exception is not granted the ramp would have to be reconstructed to a max 12% super-elevation for a 2-lane ramp and a min. spiral length of 240'. This would be a substanstial increase in the projects scope. Design phase impacts would be additional PE cost and design schedule for design/re-design. | Active | 10% | 75 | 88 | 100 | 8.7833 | 2 | 3 | 4 | 0.3 | 7 | 3 | Avoid | Roadway Designer | 1) Conduct pre-coordination with SPDB to obtain buy-off to minimize the likelihood of rejection. 2) Provide updates/coordination with SPDB as design progresses. 3) Document necessary information regarding Design Exceptions to facilitate communications/understanding. 4) Manage internal resources to ensure timelines for submittals can be achieved. | 3750 | 8.7833 | 15000 | #REF! | #REF! | #REF! | Mitigate | Enhance |  | 2026-05-19
K1234 | 2 | 2021-06-01 | Design Exception Approval | CN | yes | Threat | The project assumes design exception approval for substandard super-elevation of 13% and a substandard spiral length of 200' for the Exit 400 SB off ramp. If the design exception is not granted the ramp would have to be reconstructed to a max 12% super-elevation for a 2-lane ramp and a min. spiral length of 240'. This would be a substanstial increase in the projects scope. Construction phase impacts include reconstructing the ramp and lengthing the spiral. This would trigger widening of the hwy 999 o'xing structure. | Active | 10% | 2500 | 3750 | 5000 | 375 | 2 | 3 | 4 | 0.3 | 1 | 3 | Avoid | Roadway Designer | 1) Conduct pre-coordination with SPDB to obtain buy-off to minimize the likelihood of rejection. 2) Provide updates/coordination with SPDB as design progresses. 3) Document necessary information regarding Design Exceptions to facilitate communications/understanding. 4) Manage internal resources to ensure timelines for submittals can be achieved. | 125000 | 375 | 750000 | #REF! | #REF! | #REF! | Avoid | Exploit
K1234 | 3 | 2021-06-01 | Bidding Climate - Volume of Work | CN | no | Threat | High quantity of ODOT statewide projects being bid for 2022 construction may result in higher than expected bid prices due to capacity of industry and availability of contractors. | Active | 50% | 100 | 550 | 1000 | 275 | 0 | 0 | 0.01 | 0.00083333 | 2 | 8 | Mitigate | TPM | 1) Coordinate with Constructability Review program to engage AGC on direct project review and comment 2) Conduct evaluation of anticipated material volumes for timing of construction and perform outreach to suppliers. | 45000 | 275 | 550000 | #REF! | #REF! | #REF! | Accept | Accept
K1234 | 4 | 2021-06-01 | Value Engineering Study @ 100% Design | CN | yes | Opportunity | VE studies on average reduce project cost 20% and commonly produces construction schedule savings. If a VE study is conducted then the project cost and schedule may decrease. | Retired | 50% | 0 | 2500 | 5000 | 0 | 0 | 3 | 6 | 0 |  |  | Enhance | TPM | Coordinate with VE program to conduct value engineering study. | 0 | 0 | 2750000 | #REF! | #REF! | #REF! | Transfer | Transfer
K1234 | 5 | 2021-06-01 | High Water Table & Stormwater Facilities | PE | yes | Threat | Design deviation is being pursued for the construction of water quality and quantity facilities within a known high water table. If not approved, other off-site facilities that require ROW would need to be considered. The driver of the high-end costs are acquisitions of additional ROW to construct additional treatment facilities. In terms of schedule, an additional 12 months could be incurred for the additional ROW acquisitions. | Active | 30% | 0 | 300 | 600 | 90 | 0 | 6 | 12 | 1.8 | 3 | 1 | Avoid | Hydro Lead | 1) Hydro team to submit design deviation for water table depth at water quality and detention facilities. 2) ODOT and Consultant Design team to coordinate on format and information to be provided as part of design deviation information. Updates to be incorporated to facilitate reviews and approval. | 0 | 90 | 210000 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 6 | 2021-06-01 | Utility Potholing | PE | yes | Threat | Potholing is currently scheduled; however, the required data for utility owners may not be received in time. The risk is that the utility owners do not complete the potholing in a timely manner to support the project design development. This will result in additional cost to the project for potholing to capture the data. | Active | 10% | 15 | 18 | 20 | 1.7833 | 0 | 1 | 1.01 | 0.0835 | 8 | 7 | Mitigate | Utilities | 1) Utility Coordinator actively working with utilities on potholing efforts. 2) Engage in regular communication/coordination on utilities where there is a need for potholing/information. | 750 | 1.7833 | 3000 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 7 | 2021-06-01 | Contract Length of Deep Foundations | CN | no | Threat | Foundation lengths have been assumed to be a certain length and may not meet the formal recommendations being developed and to be provided regarding Geotechnical capacity. This could result in an increased foundation length, thereby increasing project costs. | Active | 70% | 0 | 25 | 50 | 17.5 | 0 | 1 | 2 | 0.7 | 6 | 2 | Mitigate | Geotech Lead | 1) Coordination and communication between Geotechnical and Structures for SB lanes in order to develop correct foundation lengths. 2) Once determination is made, update estimate accordingly and retire risk. | 0 | 17.5 | 37500 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 8 | 2021-06-01 | Stormwater Facility Sizing | CN | yes | Threat | Further refinement of water quality and detention facility design may cause increases in facility cost. This could include the introduction of an additional detention facility. The risk is that the plan does not materialize as intended for the subsurface detention facility and there is a need to introduce an additional detention facility on the south side of ODOT Blvd. This item is affected by roadway design element updates, hydro resourcing, and project construction schedule. Considered construction risk only as design schedule should be able to absorb additional design. | Active | 30% | 50 | 150 | 250 | 45 | 0 | 1 | 2 | 0.3 | 4 | 3 | Mitigate | Hydro Lead | 1) Finalize roadway design including pavement sawcut lines; allow sufficient time for hydraulics design. 2) Continue to analyze and revise the tank design for the subsurface stormwater detention facility, including costs/benefits of proprietary tank vendors. 3) Explore options and seek to identify approaches to reduce the size of the tank requirements. | 12500 | 45 | 87500 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 9 | 2021-06-01 | 1'' Grind and Inlay | CN | yes | Threat | The 1-inch grind and inlay may suffer pavement delamination during grind of partial lift of pavement or delamination of new pavement. This would be due to inadequate bond between new and existing ACP resulting in contract change orders and/or delays to repair pavement and additional traffic impacts. Delays are at the tail end of the construction season and would push a season. The recent lift of pavement was completed in 2013. Note that the project is already calling out the use of a fine milling head. | Active | 10% | 50 | 383 | 715 | 38.2833 | 1 | 4 |  | 0.28333 | 5 | 6 | Accept | Resident Engineer | 1) If issues emerge, use a temporary patching operation to address the issue until the next paving season. | 2500 | 38.2833 | 107250 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 10 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 11 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 12 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 13 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 14 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 15 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 16 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 17 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 18 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 19 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 20 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 21 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 22 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 23 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 24 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 25 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 26 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 27 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 28 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 29 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 30 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 31 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 32 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 33 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 34 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 35 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 36 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 37 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 38 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 39 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 40 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 41 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 42 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 43 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 44 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 45 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 46 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 47 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 48 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 49 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 50 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 51 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 52 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 53 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 54 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 55 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 56 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 57 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 58 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 59 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 60 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 61 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 62 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 63 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 64 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 65 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 66 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 67 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 68 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 69 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 70 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 71 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 72 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 73 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 74 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 75 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 76 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 77 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 78 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 79 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 80 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 81 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 82 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 83 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 84 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 85 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 86 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 87 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 88 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 89 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 90 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 91 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 92 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 93 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 94 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 95 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 96 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 97 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 98 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 99 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 100 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 101 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 102 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 103 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 104 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 105 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 106 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 107 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 108 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 109 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 110 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 111 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 112 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 113 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 114 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 115 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 116 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 117 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 118 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 119 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 120 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 121 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 122 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 123 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 124 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 125 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 126 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 127 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 128 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 129 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 130 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 131 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 132 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 133 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 134 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 135 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 136 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 137 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 138 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 139 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 140 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 141 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 142 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 143 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 144 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 145 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 146 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 147 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 148 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 149 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
K1234 | 150 | [11 empty] | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | #REF! | #REF! | #REF! | Mitigate | Enhance
Guidance:
Proper use of this tool assumes familiarity with Project Risk Management concepts. A guide has been developed to assist users in managing project risks:
https://www.oregon.gov/odot/Engineering/Pages/VE-RM.aspx
https://www.oregon.gov/odot/Engineering/Docs_RMVE/Managing-Project-Risks-ODOT-STIP.pdf