## Upcoming RW Projects
Region | Key Number | Work Types | Section | Applicant | Counties | Description | RW Cost | RW YR | Monitor Code | Status | Admin By
1 | 19358 | MODERN | Basalt Creek Ext: Grahams Ferry Rd-Boones Ferry Rd | WASHINGTON COUNTY | WASHINGTON | Construct a new arterial roadway providing industrial freight access in the Basalt Creek planning area. The extension of the parkway is an east-west alignment crossing the Seely Ditch with a 600ft long bridge. | 4001000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
4 | 20073 | SAFETY | US20 (Greenwood Ave): 1st St to 6th St (Bend) | CITY OF BEND | DESCHUTES | This project will design active transportation needs on Greenwood Avenue (1st to 6th Street; crossing of 3rd Street; to include signal changes as required) to improve safety for the traveling public. | 500000 | 2027 | ROWACQ | Land Purchase 2027 | ODOT/LOCAL
4 | 20378 | BRIDGE | Archie Briggs Rd (Deschutes River) Bridges | CITY OF BEND | DESCHUTES | Replace bridges 17C05 & 17C040 with ones that meet current standards. | 66893.31 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
1 | 20488 | BRIDGE | North Dakota Street: Fanno Creek Bridge | CITY OF TIGARD | WASHINGTON | Construct a new single span bridge on the same alignment because the existing bridge is failing. Raise the vertical grade line to improve site distance approaching the railroad crossing. | 1611843 | 2027 | ROWACQ | Land Purchase 2027 | ODOT/LOCAL
3 | 21017 | CMAQ | West Pine St reconstruction | CITY OF CENTRAL POINT | JACKSON | Add sidewalk; curb & gutter; bike lanes; 2 travel lanes and a central lane for vehicles from both directions to wait and make left turns. | 800000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 21185 | SAFETY | Queen Avenue Rail Crossing (Albany) | RAIL DIVISION | LINN | Upgrade existing railroad warning devices to improve pedestrian safety. | 285000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | RAIL
1 | 21629 | SAFETY | SE Division St: 148th Ave - 174th Ave (Portland) | CITY OF PORTLAND | MULTNOMAH | Convert existing two-way left turn lane to a raised median to improve safety on this section. | 45000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 21633 | SAFETY | SW Shattuck Rd at OR10 (Portland) | CITY OF PORTLAND | MULTNOMAH | Rebuild traffic signal to increase visibility and accommodate left turn signal heads and phases on Shattuck Road to improve safety at this intersection. | 36612 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 21635 | SAFETY | SE Flavel St at 72nd Ave (Portland) | CITY OF PORTLAND | MULTNOMAH | Rebuild the traffic signal adding left turn capability and add lighting to improve safety at this intersection. | 40000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
3 | 21728 | SAFETY | Crater Lake Ave Signal Improvements (Medford) | CITY OF MEDFORD | JACKSON | Install retroreflective backplates at 8 signalized intersections. Install flashing lights at the intersections of Minnesota Ave; Grand Ave; and Bradbury St with a ped refuge island at Bradbury. Replace the signal at Brookhurst St to include east/west left turn pockets; replace all permissive left turn phasing and relocate a refuge island; modify the signal at Roberts Rd N to replace five section "doghouse" signal heads. Upgrade ADA. | 100000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 21890 | BIKPED | Commercial St SE: Vista St to Ratcliff Dr (Salem) | CITY OF SALEM | MARION | Construct sidewalks and protected bike lane along the east side of Commercial Street SE and add a new signal at Ratcliff to increase safety. | 320000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
5 | 22017 | BRIDGE | Holbrook Creek Road: Pine Creek bridge (Baker County) | BAKER COUNTY | BAKER | Replace a bridge that was previously washed out. Modify the river bed to prevent future flood events from washing the bridge out again. | 25000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 22032 | BRIDGE | South Myrtle Road: South Myrtle Creek bridge | DOUGLAS COUNTY | DOUGLAS | Design to replace the existing bridge with a new bridge that meets current design standards. | 47305 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
1 | 22128 | BIKPED | Aloha Access Improvements: SW 174th Ave - SW 187th Ave | WASHINGTON COUNTY | WASHINGTON | Design and implement various access and crossing enhancements in the Aloha Town Center area to improve pedestrian safety. | 613253 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22138 | BIKPED | Stark & Washington Safety: SE 92nd Ave - SE 109th Ave | CITY OF PORTLAND | MULTNOMAH | Construct protected bike lanes; protected signal phasing for pedestrians and bicyclists; pedestrian crossing; transit islands to improve transit operations and comfort; pedestrian islands to shorten crossing distance; paving; and signal controller upgrades to better manage speeds and traffic flow. | 800000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22176 | TR-CAP | Bus Layover & Operator Facility Upgrades/Acquisition TriMet | TRIMET | CLACKAMAS, MULTNOMAH, WASHINGTON | Funding to build a permanent off-street; bus layover facility; which will add up to nine 60-foot layover spaces for TriMet buses; improve operator safety; support mixed-use urban redevelopment and satisfy a 2016 city of Portland commitment related to the Powell-Division transit & development project and related locally preferred alternative. Funds will also be used to provide additional/improved break facilities for TriMet bus operators. | 7000000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL
3 | 22278 | BIKPED, CMAQ | Clay Street: Faith Ave to Siskiyou Blvd | JACKSON COUNTY | JACKSON | Install bike and pedestrian facilities with curb; gutter; sidewalk and drainage to facilitate the addition of the bike and pedestrian facilities. | 1205000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 22346 | CMAQ | West Bank Path extension (Eugene) | CITY OF EUGENE | LANE | Extend West Bank shared-use Path north from Hunsaker St to Admirals St; adding sidewalk to Admiral St and enhanced crosswalks at River Loop 1 and Wilkes Drive crossings to reduce congestion and improve air quality. | 50000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22460 | BIKPED | Berkeley Park Path (Eugene) | CITY OF EUGENE | LANE | Construction of an approximately 0.13 mile path through Berkeley Park; connecting Wilson St to a higher density housing development parking lot and then connecting to Fern Ridge Trail through the park. The path will improve access and safety for people walking and biking through the area. | 20000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22596 | MODERN | Franklin Blvd A Partnership to Rebuild and Revive a Corridor | CITY OF EUGENE | LANE | The Franklin Boulevard Transformation project will provide a multi-modal complete street across both cities of Eugene and Springfield to better serve the facility's users. From 11th Ave in Eugene to Mississippi Ave in Springfield. Work includes repaving the street; reduce travel lanes; construct bikeways on both sides of the street; construct a dedicated bus lane; add roundabouts to key intersections; and reconstruct sidewalks and sidewalk access ramps. The project will also include traffic signal work at select intersections; lighting; stormwater facilities; and landscaping. | 2500000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL
2 | 22596 | MODERN | Franklin Blvd A Partnership to Rebuild and Revive a Corridor | CITY OF SPRINGFIELD | LANE | The Franklin Boulevard Transformation project will provide a multi-modal complete street across both cities of Eugene and Springfield to better serve the facility's users. From 11th Ave in Eugene to Mississippi Ave in Springfield. Work includes repaving the street; reduce travel lanes; construct bikeways on both sides of the street; construct a dedicated bus lane; add roundabouts to key intersections; and reconstruct sidewalks and sidewalk access ramps. The project will also include traffic signal work at select intersections; lighting; stormwater facilities; and landscaping. | 2500000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL
2 | 22596 | MODERN | Franklin Blvd A Partnership to Rebuild and Revive a Corridor | LANE TRANSIT DISTRICT | LANE | The Franklin Boulevard Transformation project will provide a multi-modal complete street across both cities of Eugene and Springfield to better serve the facility's users. From 11th Ave in Eugene to Mississippi Ave in Springfield. Work includes repaving the street; reduce travel lanes; construct bikeways on both sides of the street; construct a dedicated bus lane; add roundabouts to key intersections; and reconstruct sidewalks and sidewalk access ramps. The project will also include traffic signal work at select intersections; lighting; stormwater facilities; and landscaping. | 2500000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL
3 | 22638 | BRIDGE | Arizona Ranch Rd: Myrtle Creek Bridge | CURRY COUNTY | CURRY | Replace the bridge with a wider and modern bridge to increase safety and improve access. | 6300 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 22639 | BRIDGE | Days Creek Rd: Days Creek Bridge | DOUGLAS COUNTY | DOUGLAS | Replace the bridge to restore load rating and access for all vehicles. | 47305 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 22640 | BRIDGE | South Deer Creek (Hatfield Truss) | DOUGLAS COUNTY | DOUGLAS | Replace the existing structure with a new bridge that meets current standards. | 47305 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 22655 | BRIDGE | Newton Creek Bridge | CITY OF ROSEBURG | DOUGLAS | Replace bridge to restore load rating and access for all vehicles. | 12700 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 22656 | BRIDGE | Luckiamute River; Helmick Road bridge (Polk Co) | POLK COUNTY | POLK | Rehabilitation of bridge including a phase 1 seismic retrofit; erosion control repair; and other general maintenance needs to preserve the historic integrity of the bridge. | 50700 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/COBO
2 | 22657 | BRIDGE | Dougherty Slough; Blum Lane; Prince bridge (Tillamook Co) | TILLAMOOK COUNTY | TILLAMOOK | Replace the bridge in order to meet current bridge standards. | 160000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 22696 | SAFETY | Virginia/Daisy Ave.: 32nd St. to Bob Straub Parkway (Springfield) | CITY OF SPRINGFIELD | LANE | Design and install various pedestrian and bicycle treatments consistent with a bicycle boulevard on Virginia Avenue/Daisy Avenue. These treatments include improvements to pedestrian crossings; speed bumps and adding bike lane pavement markings. | 102000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22701 | SAFETY | Division Avenue Roundabouts Corridor (Eugene) | CITY OF EUGENE | LANE | Design and construct two roundabouts on Division Avenue (from River Road to 400 feet southeast of Lone Oak Way) to include additional speed reduction features; travel lane reductions; crossing improvements; and protected bike lanes. This roundabout project includes enhancements that support people walking and biking at this location that will increase safety. | 750000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22753 | PRESRV | Clear Lake Rd and Airport Rd: pavement preserv. (Eug) | LANE COUNTY | LANE | Pavement preservation along Clear Lake Rd from Highway 99 to the urban boundary (approximately at Lakeview Dr) and along Airport Rd from approximately 460' east of where it diverges from Old Airport Rd and approximately 250' north of the intersection at Northrop Dr. This project will prevent more costly repairs in the future and promote safety. Project includes speed treatments; safety countermeasure. On Clear Lake Rd the project includes operational upgrades at Green Hill Rd intersection including rehabilitation of conduits and junction boxes; and a signal upgrade. On Airport Rd the project includes safety treatments at the Green Hill Rd intersection including reconfiguration of the Green Hill Rd approach; elimination of the right turn lane and the addition of a receiving lane to reduce crash severity. | 25000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22780 | SAFETY | Bailey Hill Rd and Bertelsen Rd roundabout (Eugene) | CITY OF EUGENE | LANE | Project will construct a roundabout with accompanying bicycle and pedestrian facilities at the intersection of Bailey Hill Rd and Bertelsen Rd to reduce vehicle speeds at the intersection and continuing on to more dense areas of Eugene. | 222890.89 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22781 | BRIDGE | Goodpasture Island Rd Bridge seismic retrofit (Eugene) | CITY OF EUGENE | LANE | Project will strengthen the existing bridge on Goodpasture Island Rd over the Delta Highway (bridge number 09359) to reduce the structure's vulnerability during a seismic event. | 10000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22825 | SAFETY | SE Cesar Chavez Blvd: Lafayette Ct - Schiller St (Portland) | CITY OF PORTLAND | MULTNOMAH | Reduce this section from 4 to 3 lanes (one in each direction and a center turn lane). Add north-south left-turn lanes on SE Chavez at SE Raymond St. Rebuild the signal at SE Holgate to protect left turns. Relocate the bus stop at SE Holgate St closer to the crosswalk. | 20000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22826 | SAFETY | NE Cornell Rd at 17th Ave and 21st Ave | WASHINGTON COUNTY | WASHINGTON | Restrict the 17th Ave intersection to right in right out only and install a signal at the 21st Ave intersection. Install streetlights at both locations. | 150000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22827 | SAFETY | 92nd Ave; E Burnside St and N Basin Ave (Portland) | CITY OF PORTLAND | MULTNOMAH | Signal; signage and lighting & pavement marking upgrades including curb extensions; raised medians to improve visibility and safety at the intersections of SE 92nd Ave at SE Division St; E Burnside at 122nd and 148th Ave; and on N Basin St between N Emerson St and N Leverman St. | 47000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22829 | SAFETY | Lake Oswego Signals Visibility Upgrades | CITY OF LAKE OSWEGO | CLACKAMAS, MULTNOMAH | Signal upgrades to improve visibility and safety at various locations. Install leading pedestrian intervals and changes from permissive-only green left turn signals to flashing yellow arrows. | 5000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
1 | 22831 | SAFETY | SE Foster Rd: 101st Ave - 136th Ave | CITY OF PORTLAND | MULTNOMAH | Install speed feedback signs; additional lighting and raised pavement markers to improve safety. | 12000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22832 | SAFETY | Gresham Pedestrian Improvements | CITY OF GRESHAM | MULTNOMAH | Install crosswalks with flashing lights; stop bars and signs to improve safety. Install curb ramps to meet current standards. | 20000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
3 | 22846 | SAFETY | N Columbus Ave at W Jackson St Roundabout (Medford) | CITY OF MEDFORD | JACKSON | Construct a roundabout at the intersection of North Columbus Avenue and Jackson Street in the city of Medford to reduce the number and severity of intersection crashes. | 173702 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 22860 | SAFETY | Pine Street Signal Improvements (Central Point) | CITY OF CENTRAL POINT | JACKSON | Intersection updates that may include signal upgrades; install a right-turn signal and pedestrian crossing on the northbound right turn lane at Pine;10th and Freeman Street to provide a safer route for the traveling public. | 46912 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 22946 | SAFETY | Beta Drive SW Rail Crossing (Albany) | RAIL DIVISION | LINN | Complete design to install light and gates and improve humped crossing to standard to improve safety and reduce incidents at crossings. | 192603 | 2027 | ROWACQ | Land Purchase 2027 | RAIL
1 | 23083 | BRIDGE | S Holly Lane: Abernethy Creek Bridge | CLACKAMAS COUNTY | CLACKAMAS | Replace the existing bridge with a new single-span bridge to ensure continued connectivity. | 126700 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 23125 | BRIDGE | Willamette River and Independence bridge | MARION COUNTY | POLK | Strengthen the bridge to increase the load rating and perform other general repairs and maintenance to preserve the bridge. | 88700 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 23134 | BRIDGE | Murder Creek (Nygren Road) bridge (Linn Co) | LINN COUNTY | LINN | Rehab existing bridge to include installing erosion protection; add new pavement; replace bridge rail and other general maintenance needs to maintain bridge integrity. | 25300 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 23140 | BRIDGE | Truax Creek (Clover Ridge Road) bridge (Linn Co) | LINN COUNTY | LINN | Replace the bridge to meet current standards. | 95000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
3 | 23161 | BRIDGE | Althouse Creek (Takilma Road) bridge | JOSEPHINE COUNTY | JOSEPHINE | Replace the existing bridge to meet current standards. | 111800 | 2027 | ROWACQ | Land Purchase 2027 | ODOT/LOCAL
3 | 23163 | BRIDGE | Galls Creek (Lampman Rd) bridge | JACKSON COUNTY | JACKSON | Replace the existing bridge to meet current standards. | 63300 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
1 | 23242 | BIKPED | Willamette Falls Dr: 16th St - Ostman Rd Ped/Bike Upgrades | CITY OF WEST LINN | CLACKAMAS | Install grade separated bike facilities; pedestrian crossings; bus stops and access to transit facility; and intersection treatments prioritizing pedestrian visibility and protection. | 400000 | 2027 | ROWACQ | Land Purchase 2027 | ODOT/LOCAL
1 | 23245 | BIKPED | 162nd Ave ped/bike upgrades: NE Glisan to NE Halsey | GRESHAM | MULTNOMAH | Complete street safety elements including arterial rehabilitation; ADA ramps; and crossings; pedestrian sidewalk and buffered bike lane construction to 162nd Ave from NE Glisan St north to NE Halsey St for increased pedestrian and bicyclist safety. | 239112 | 2026 | ROWACQ | Land Purchase 2026 | LOCAL/CERT
1 | 23246 | BIKPED | NE Sandy Blvd: NE 201st Ave to Quail Hollow mobile home park | MULTNOMAH COUNTY | MULTNOMAH | Construct and install bicycle facilities; sidewalks & pedestrian crossings; plus transit access amenities to increase comfort; safety; and access for all modes. | 434999 | 2027 | ROWACQ | Land Purchase 2027 | LOCAL
1 | 23254 | CMAQ | Council Creek Regional Trail: Enhanced Pedestrian Crossings | WASHINGTON COUNTY | WASHINGTON | Complete 20 street and driveway crossings along the Council Creek Regional Trail corridor to facilitate safe; convenient; and comfortable connections for people walking; biking or rolling between the centers of Forest Grove; Cornelius and Hillsboro. Trail portion being delivered under project key 23549. | 100000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
3 | 23303 | CMAQ | Table Rock Rd: Merriman to I-5 | CITY OF MEDFORD | JACKSON | Add sidewalks; bike lanes; center turn lane and lighting to provide a safer travel experience for pedestrians and bicycles on the roadway. | 1000000 | 2027 | ROWACQ | Land Purchase 2027 | ODOT/LOCAL
3 | 23304 | BIKPED, CMAQ | Lincoln Rd Multi-Modal and Transit Enhancement | CITY OF GRANTS PASS | JOSEPHINE | Design and acquire right-of-way to modernize Lincoln Rd from Bridge to G St; including new bike lanes and sidewalks. Work also includes adding a turn lane and resurfacing existing lanes. | 2265016 | 2027 | ROWACQ | Land Purchase 2027 | ODOT/LOCAL
1 | 23459 | BRIDGE | SE Bull Run Rd: Bull Run River Bridge | CLACKAMAS COUNTY | CLACKAMAS | Design and right of way acquisition to replace the existing bridge to ensure continued connectivity. | 250000 | 2027 | ROWACQ | Land Purchase 2027 | LOCAL/CERT
4 | 23494 | BIKPED | Hawthorne Ave Pedestrian & Bicyclist Overcrossing (Bend) | CITY OF BEND | DESCHUTES | Provide safe access for pedestrians and bicyclists by designing and constructing a bridge over US97 and BNSF railroad connecting east Hawthorne Avenue to downtown Bend. | 1200000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 23503 | BIKPED | Mill Creek Greenway Trail System (Woodburn) | CITY OF WOODBURN | MARION | Design and construct two new trail segments to connect existing Mill Creek Trail System. Settlemier Park and Hermanson Pond Trail Extension. The paths will improve access and safety for people walking and biking. | 167168.17 | 2026 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 23504 | BIKPED | Pringle Creek Path Connection (Salem) | CITY OF SALEM | MARION | Construct missing segment of Pringle Creek Path along the north bank of Pringle Creek connecting existing Pringle Creek paths and Salem Civic Center to Riverfront Park and to paths that extend from there to Minto Island and west Salem. The path will improve access and safety for people walking and biking. | 134550 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 23505 | BIKPED | Gresham Park Paths: Columbia View Park and N. Gresham Park | CITY OF GRESHAM | MULTNOMAH | Construct an approximately 800 foot multi-use path across Columbia View Park; and an approximately 1;400 foot multi-use path across North Gresham Park. Both paths will provide pedestrian and local bicycle connectivity and school access. | 6000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 23556 | BIKPED | 122nd Ave Safety Upgrades: Sandy Blvd to Foster Rd | CITY OF PORTLAND | MULTNOMAH | Safety improvements on 5.5 miles of 122nd Avenue from Sandy Blvd south to Foster Rd including: street lighting upgrades; 4 miles of protected bike lanes; pedestrian/bicycle signal upgrades; reducing vehicle lanes; adding pedestrian crossings; adding raised medians; landscaping; bus stop curb extensions; speed reader boards with automated enforcement and a roundabout. | 125000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL
2 | 23573 | OPERAT | Shaw Creek crossing culvert replacement; Siuslaw Rd; Lane Co | LANE COUNTY | LANE | Install new fish passage near mile point 36.8 on Siuslaw Road which is under threat of failure due to the nature of an existing culvert stream crossing at Shaw Creek; a tributary to the main stem of the Siuslaw River to open up nearly five miles of salmon spawning habitat. | 15000 | 2026 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 23574 | CULVRT | Beaver Creek Fish Passage Restoration at Troutdale Rd | MULTNOMAH COUNTY | MULTNOMAH | Design; right-of-way acquisition; and permitting for the replacement of the existing Troutdale Rd culvert and fish ladder on Beaver Creek with a new at-grade bridge. | 125000 | 2026 | ROWACQ | Land Purchase 2026 | LOCAL/CERT
1 | 23578 | CULVRT | Conway Creek at Aschoff Rd culvert replacement | CLACKAMAS COUNTY | CLACKAMAS | Design and construction to replace existing culverts carrying Conway Creek under Aschoff Road in Rhododendron in Clackamas County. | 103000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 23625 | SAFETY | Main Avenue/OR 104 Pedestrian Route (Warrenton) | CITY OF WARRENTON | CLATSOP | Design and construct pedestrian updates to the existing roadway to improve safety. | 624094.51 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 23689 | CULVRT | Fruitdale Drive: Fruitdale Creek | ODOT | JOSEPHINE | Replace substandard culvert to meet current fish passage needs. Project will include active transportation and ADA updates to meet current design requirements. | 215300 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
1 | 23759 | MODERN | Washington Street: Metro South - Abernethy Rd | CITY OF OREGON CITY | CLACKAMAS | Project to modernize road systems and provide easier; safer access to community; retail; and entertainment facilities. Construction of center turn lane; pedestrian level street lighting; sidewalks and planter/stormwater treatment area. Installation of a flashing light at high volume pedestrian crossing area. | 130000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 23778 | EM-REL | Sandlake Road Slide (MP 10.6) (Tierra Del Mar) | TILLAMOOK COUNTY | TILLAMOOK | Restore the southbound lane of Sandlake Road south of Tierra Del Mar which was undermined as a result of a landslide. This is permanent emergency relief repairs. | 5000 | 2026 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
4 | 23801 | SAFETY | Warm Springs Commercial Corridor Safety Project | CONFEDERATED TRIBES OF WARM SPRINGS | JEFFERSON | This project will design and construct improvements to the US 26 corridor in Warm Springs. Improvements will include speed reduction treatments in downtown Warm Springs; a new roundabout at the intersection of US26 and Paiute Avenue/BIA 3; a shared-use path on both sides of the highway; and access to existing transit stops. | 1300000 | 2027 | ROWACQ | Land Purchase 2027 | ODOT/LOCAL
2 | 23874 | OPERAT | Mill Creek--Brickyard Road AOP barrier (Tillamook) | TILLAMOOK COUNTY | TILLAMOOK | Remove two Aquatic Organism Passage (AOP) fish passage barrier culverts carrying Mill Creek and Mill Creek Trib B under Brickyard Road and replace with fish passage friendly structures. | 132750 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL
2 | 23895 | BRIDGE | Godsey Road: North Fork Ash Creek Bridge (Dallas) | CITY OF DALLAS | POLK | Design and right of way acquisition for a future bridge replacement; to ensure continued connectivity. | 10000 | 2026 | ROWACQ | Land Purchase 2026 | LOCAL
1 | 23909 | SPPROG | Canby (M.J. Lee) Ferry Ramp Enhancements | CLACKAMAS COUNTY | CLACKAMAS | Project will evaluate stabilization of the south ramp and replace the north ramp landing and stabilize the embankment. Ramps are used by the Canby Ferry which provides an important link across the Willamette River between Canby & Wilsonville/West Linn. Ramp replacement and bank stabilizations are needed to protect the roadway above the riverbank (SW Mountain Rd). | 20000 | 2027 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 24000 | OP-SLD | SE Gordon Creek Road slope stabilization at MP 2.1 | MULTNOMAH COUNTY | MULTNOMAH | Slope stabilization on SE Gordon Creek Road at 2.1 miles south of SE Hurlburt Road . The project will provide permanent repairs to an historically known slide area; where a large rock and debris slide on February 1; 2024 closed the roadway and required extensive emergency repairs. | 50000 | 2026 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 24116 | EM-REL | Kaiser Road over Abbey Creek Embankment Repair | MULTNOMAH COUNTY | MULTNOMAH | Embankment repair of the east side of NW Kaiser Road from rising Water on Abbey Creek. | 50000 | 2026 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
3 | 24445 | EM-REL | Tiller Trail Hwy; MP 43.1 | JACKSON COUNTY | JACKSON | Repair will consist of slope stability study; rebuild ditches and culverts to restore drainage; stabilize the embankment; and add stone embankment under the full highway width. | 10000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 24446 | EM-REL | Tiller Trail Hwy; MP 44.1 | JACKSON COUNTY | JACKSON | Repair will consist of slope stability study; rebuild ditches and culverts to restore drainage; and stabilize the embankment. | 10000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 24447 | EM-REL | Tiller Trail Hwy; MP 44.7 | JACKSON COUNTY | JACKSON | Repair will consist of slope stability study; rebuild ditches and culverts to restore drainage; stabilize the embankment and lower the grade if possible. | 10000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL