## Slide 1
CONNECTING TO
COLLECTIONS
Planning for Success
Choosing the Right Project
Notes: Introduce Self
Mentor Corps Project
Past experience at defining and completing short-term collections projects. Feedback from the first audience was that more examples is better. Some successes, some failures
Get a feel for who is in the audience. Anyone use the MentorCorps project before?
Any potential Mentors in the room?

## Slide 2
Why Create a Project?
• To focus your staff’s energy
• To focus fundraising efforts
• To satisfy the interests of a donor
• To fulfill your institutional mission
Notes: You create a project to satisfy a need.
The needs remain the same but change in importance occasionally. If you have a pressing need to address the interests of a particular donor, the needs of your staff may take a back seat to that for a short time. If your institution has a larger goal ahead, a merger, a move to new space, then other issues fade into the background temporarily.
Defining a single project focuses the resources you do have toward the accomplishment of a single goal.
We all have a lot to do, but if each of my staff could spend a couple hours a week organizing the new exhibit preparation room, we could get that done.
Each of us does what we can to bring in donors and money, but if we all work together on the annual gala, we could bring in our operating expenses for the year.
Jane and John Doe are ready to give us their paperclip collection, but not unless we create permanent storage space to catalog and house it.
Out mission exhorts us to create intercultural dialogue, the current exhibit on immigration routes will do that, but we need to launch an oral history project to record the immigration stories.
Your organization does so much. The project you are creating helps to focus the attention and energy of your staff and volunteers on a single need temporarily

## Slide 3
That Brainstorming Session
Where do you go from here?
Notes: Did you and your stakeholders brainstorm the 20 projects you would like to see accomplished in your collection this year? Do you have a system established whereby you revisit your needs on a regular basis with staff, board, volunteers, and other stakeholders? Where you write down what you would like to accomplish in your collection? Do you reach outside of your board and staff for those ideas? Volunteers often have great insight into what the collection needs most.
Every shop has a thousand things that need to be accomplished. Some of them are just the day-to-day tasks of doing the job – registering, arranging, cataloging, storing.
When do these tasks become a Project? Start with your wishlist.
Take a moment now to think of seven things that need doing where you work. Long-term, short-term, vague or specific.

## Slide 4
Choosing a Project
1st photo caption goes here
Notes: So you have thought of a few possibilities. You will think of some more.
This presentation covers how to choose from among them, plan to implement them, and prepare to execute a project in your collection.
You then must be able to articulate what makes that collection special – how you and your team are uniquely suited to caring for it, and how can you prove there is a larger need in the world for the work to be done.
Not every project on the brainstorming drawing board should get started. Don’t spend the time on a project when you find you are answering these questions in ways you don’t like.

## Slide 5
Planning for Success
A Successful Project must:
• Have definable objectives
• Draw on attainable resources
• Be finite and temporary
Notes: A good project must have clearly stated objectives; it must be within your institution’s resources; and it must have start and end dates,
It must be temporary and not part of routine collections care. It must result in something you didn’t have before you began.
1.Objective – we talked about your institutional goals back a few slides ago. Goals are broad and not closely defined. Our institution’s goals is to foster intercultural dialog. That’s a big goal. Objectives are more closely defined. The objective of your collections project is almost a reiteration of your project title. “Cataloging the netsuke collection”, “Rehousing the Johnson Papers”, “Painting all the books shiny brown.”
2. Resources- keep in mind that you don’t necessarily have to HAVE all the resources you need. You just need to be able to get them. Staff, (temporary staff) consultants, supplies, money…
3. Finite and temporary – “dusting the collection” isn’t going to fly, “inventorying the collection” is not going to fly. Things that you have to do on a regular basis just to keep the doors open aren’t really projects. They are maintenance. Being able to say “at the end of this project, all the netsukes will be in industry standard housings, with condition reports completed, and catalog numbers affixed” That is something that wasn’t true when you started the project and it has an definable moment at which you will be able to say, “We’re done here.”
Eliminate from your brainstormin lists any ongoing projects – things you anticipate always having to do. Eliminate anything from the list that you cannot state, in single sentence, what the objective would be beyond “not having to do it later.”
In addition to not wasting your time, or that of your volunteers, the end goal of these exercises is to determine if the project you are envisioning is feasable. If you have planned your project well, it will be fundable. Funding agencies are looking for all of the same earmarks of a successful project that you are.

## Slide 6
Project Considerations
• Resources – include people, materials, technology
• Risks – include an evaluation of the downsides
• Benefits – what will be gained?
• Methods – research professional standards and methods
• Management – who will keep this project on track?
• Environment – where will it happen, and with what?
Notes: Note: I think this slide is superfluous; not my idea.
OK, not going to define these words. Let’s talk them through and make sure they make sense to you. You will see them again here today.
These are big-picture issues – things to keep in mind as you wonder whether you should be creating a project.
This prepares you to start defining your individual project.

## Slide 7
Plan a Budget
•Staff Time
•Volunteer/Match time
•Contractors/Consultants
•Supplies
•Overhead
•Capital Expenses
•Storage needs – digital and physical
•Training
•Travel
•Contingency

## Slide 8
Break for first activity
Notes: Take 10 to 15 minutes in small groups to talk about your brainstorming lists. Use the worksheets to write down the projects that have been popping into your head while I have been talking. Talk them through – listen to what other people are hoping to accomplish and see how your projects are similar and different.

## Slide 9
Getting Specific
• Define your scope
• Create measurable objectives
• Identify your stakeholders
• Revisit your institutional mission
Notes: •Define your scope. Will this be a stand-alone project in your collection? Does it represent work that will later be done in other parts of the collection or work that has already been done elsewhere? How much will this project take on (and equally importantly: what will you NOT be addressing this time?)
•Are your goals attainable? Are they measurable? How will you measure them? Develop evaluation methods right along side of your goals.
•Who cares about this project? How will you get the word out that you have accomplished it? ENVISION YOUR END GAME at the beginning.
• SOMETHING ABOUT STAKEHOLDERS
•Review your mission. Does this project move your institution in that direction?
Get specific by asking the right questions at the outset (next slide)

## Slide 10
Ask the
Right Questions
Ask your team and yourself:
• How much will we do?
• Who will do it?
• Can we complete the work?
• Why are we doing this?
Notes: I know this is repetitive, but the right way of saying it is going to get through to someone here.
Why: What are the objectives of the project? What are the projected benefits? Are your stakeholders (the people within and outside of our organization who will be affected by your result) being asked for input?
What? What is the scope, what will be included (and also importantly, what will not be included)
When? How long will this take? How will you know when you are done?
Who? Who will work on this project? Who will manage it? Who will pay for it? Who is your end user?

## Slide 11
Will It Ever End?
• How will you know when you are done?
• Are you meeting professional standards?
• Has anyone else executed a project like yours?
Notes: •Look to your previous experiences in completing collections projects. If you have none, talk to your colleagues (go to the OMA meetings, NWA meeings and create relationships with others who do similar work to you. Do not work in a vacuum.) Get a feeling for the time-frame that is acceptable for a project of your proposed scope.
• Take the time to do some research into the professional standards for what you are hoping to accomplish. These chance over time; do not assume that what you learned in school is still in practice. Read the current literature. ASK FOR HELP – Kuri and Kyle are great resources.
• Look at previously funded grant projects. Who is getting money? Are they doing something that you want to do as well? Can you learn from the way they organized their projects?

## Slide 12
Establish Standards - Be Consistent
• Cataloging Objects? Past Perfect - Nomeclature
• Processing Archives? DACS
• Library Project? MARC
• How much control is enough?
Notes: Each of our fields has cataloging standards, record-keeping standards, physical storage standards. Take the time to learn them and be compliant.
• If you are working with Past Perfect you have standardized fields to fill.
Do you have an authority file with standardized terms to fill?
• If you are processing archives establish at the outset the level to which
you are going to process. Is a Series list enough? A Box/Folder List?
Do you need to know the contents of each sheet of paper
• Be very clear about what level of intellectual control you are seeking over your collection. Over processing can bog your project down and stop you from finishing on time.

## Slide 13
Management and Oversight
Notes: • Know who you have and what their strengths and weaknesses are
• Know where to go for more expertise
• Who will volunteer? Who will supervise them?

## Slide 14
Where will we put it?
Notes: Physical and digital storage needs
Do you have the means to house this project when it is completed?

## Slide 15
Physical Projects
Does your institution have:
• Adequate physical space?
• Environmental monitoring?
• A Conservation management plan?
• A Disaster Preparedness plan?
Notes: Photograph your current space for a “before” illustration if you are planning to improve it.
Collect photographs of your storage ideals, including disaster planning implementation
How will you get from where you are to where you would like to be? Write it out – step by step.
Do you have volunteer help to design/build space for you?

## Slide 16
Digital Projects
Does your institution have:
• Adequate digital space?
• Digital storage protocols?
• Secure, off-site backup?
Notes: Is someone at your institution trained to maintain digital files to professional standards?
Be sure your storage discs are secure and backed up.

## Slide 17
“You can’t make an omelet…”
• Make a written list of supplies
• Check against existing resources
• Make a shopping list
Notes: Make sure you have what you need to work on and finish the project
• Anticipate your supply needs
• What do you have already on hand?
• What will you have to purchase?
Make a detailed list with specific needs, vendors, and prices

## Slide 18
Do Benefits outweigh Costs?
• Monetary - potential revenue, time savings,
increased donations
• Measurable – can be counted but not
translated to dollars
(website hits, visitors, historical preservation)
• Intangible – benefits that cannot be counted
(educational benefit, prestige, professional standards)
Notes: •Monetary – Benefits that can be translated into dollars. Examples are sales of a product, savings in staff time, savings in rented floor space, increased donations.
•Measurable -- These are benefits that can be counted but not translated into dollars. Examples are website hits, visitors, objects conserved.
•Intangible -- These are benefits that cannot be counted. Examples are educational benefit to visitors, prestige, quality of collection, use of standards.

## Slide 19
Well begun is half done
Notes: •Don’t be tempted to skip these steps
•Having an intuition that your project will succeed is not enough
•If you can articulate your process on paper, you can convince others of your project’s value as well as focus your resources appropriately.